## Sheet1
| Tasks | Hours
Amber | 29 | 35.75
Diego | 14 | 23
Carly | 24 | 50.75
Matthew | 22 | 93
Aidan | 16 | 34
John | 22 | 49.5

## Amber_Sprint_4
Task | Assignees | Start date | End date | Sprint | Status | Hours Completed | Corrective Action
Requirements for slides | Amber | 2024-10-03 | 2024-10-07 | Sprint 4 | Done | 0.5
Minimum Viable Product Definition | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-08 | 2024-10-15 | Sprint 4 | Done | 2
Verification Procedures | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-08 | 2024-10-15 | Sprint 4 | Done | 0.5
Drawing/SDD | Matthew, Amber | 2024-10-08 | 2024-10-15 | Sprint 4 | Done | 1.5
PSR4 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-02 | 2024-10-15 | Sprint 4 | Done | 4
GUI UI for PDR | Amber | 2024-10-15 | 2024-10-18 | Sprint 4 | Done | 0.5
Project Plan, Status, Deliverables, & Budget Analysis for PDR | Diego, Amber | 2024-10-15 | 2024-10-20 | Sprint 4 | Done | 1
Risk/Mitigation for PDR | Amber | 2024-10-15 | 2024-10-20 | Sprint 4 | Done | 1
Software/firmware for PDR | Matthew, Amber | 2024-10-15 | 2024-10-20 | Sprint 4 | Done | 2
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-21 | 2024-10-21 | Sprint 4 | Done | 1
PDR Presentation | Aidan, Carly, Diego, John, Matthew, Amber | 2024-09-24 | 2024-10-21 | Sprint 4 | Done | 2
PDR Dry Run | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-21 | 2024-10-21 | Sprint 4 | Done | 1
Preliminary Design Review Presentation | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-08 | 2024-10-22 | Sprint 4 | Done | 5
PDR Summary Slide | Amber | 2024-10-15 | 2024-10-22 | Sprint 4 | Done | 0.5
Requirements Slide PDR | Amber | 2024-10-14 | 2024-10-22 | Sprint 4 | Done | 0.5
Communication TPD Slide PDR | Amber | 2024-10-15 | 2024-10-22 | Sprint 4 | Done | 0.5
1st Order Analysis: Cameras Slide PDR | Carly, Amber | 2024-10-15 | 2024-10-22 | Sprint 4 | Done | 0.5
Project Plan to CDR Slide | Amber | 2024-10-15 | 2024-10-22 | Sprint 4 | Done | 1
Risk/Mitigation | Amber | 2024-10-15 | 2024-10-22 | Sprint 4 | Done | 1
Project Deliverable Slide | Amber | 2024-10-15 | 2024-10-22 | Sprint 4 | Done | 1
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-28 | 2024-10-28 | Sprint 4 | Done | 1
PDR Team Eval | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-22 | 2024-10-28 | Sprint 4 | Done | 1
Team Evaluation: System Requirements | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-25 | 2024-10-29 | Sprint 4 | Done | 1
Team Evaluation: Preliminary Design Review | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-25 | 2024-10-29 | Sprint 4 | Done | 1
Prototype and GUI Development | Matthew, Amber | 2024-10-21 | 2024-11-03 | Sprint 4 | Done | 2
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-04 | 2024-11-04 | Sprint 4 | Done | 1.5
Review broken down dates for PDR to CDR update | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-05 | 2024-11-05 | Sprint 4 | In Progress | 1
Scope for PDR | Amber | 2024-10-14 | 2024-11-22 | Sprint 4 | Done | 0.25
[5 empty] | Total Hours | 35.75
29

## Diego_Sprint_4
Task | Assignees | Start date | End date | Sprint | Status | Hours Completed | Corrective Action
Minimum Viable Product Definition | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-08 | 2024-10-15 | Sprint 4 | Done | 2
Verification Procedures | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-08 | 2024-10-15 | Sprint 4 | Done | 0.5
PSR4 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-02 | 2024-10-15 | Sprint 4 | Done | 4
Project Plan, Status, Deliverables, & Budget Analysis for PDR | Diego, Amber | 2024-10-15 | 2024-10-20 | Sprint 4 | Done | 1
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-21 | 2024-10-21 | Sprint 4 | Done | 1
PDR Presentation | Aidan, Carly, Diego, John, Matthew, Amber | 2024-09-24 | 2024-10-21 | Sprint 4 | Done | 2
PDR Dry Run | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-21 | 2024-10-21 | Sprint 4 | Done | 1
Preliminary Design Review Presentation | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-08 | 2024-10-22 | Sprint 4 | Done | 5
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-28 | 2024-10-28 | Sprint 4 | Done | 1
PDR Team Eval | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-22 | 2024-10-28 | Sprint 4 | Done | 1
Team Evaluation: System Requirements | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-25 | 2024-10-29 | Sprint 4 | Done | 1
Team Evaluation: Preliminary Design Review | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-25 | 2024-10-29 | Sprint 4 | Done | 1
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-04 | 2024-11-04 | Sprint 4 | Done | 1.5
Review broken down dates for PDR to CDR update | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-05 | 2024-11-05 | Sprint 4 | In Progress | 1
[5 empty] | Total Hours | 23
14

## Carly_Sprint_4
Task | Assignees | Start date | End date | Sprint | Status | Hours Completed | Corrective Action
Minimum Viable Product Definition | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-08 | 2024-10-15 | Sprint 4 | Done | 2
Verification Procedures | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-08 | 2024-10-15 | Sprint 4 | Done | 0.5
PSR4 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-02 | 2024-10-15 | Sprint 4 | Done | 4
MVP CAD drawings for PDR | Carly | 2024-10-15 | 2024-10-18 | Sprint 4 | Done | 1
Initial physical configuration for PDR | Aidan, Carly | 2024-10-15 | 2024-10-20 | Sprint 4 | Done | 1
Key components selected for PDR | Aidan, Carly | 2024-10-15 | 2024-10-20 | Sprint 4 | Done | 1
PDR Point Design CAD | Aidan, Carly, John | 2024-10-18 | 2024-10-21 | Sprint 4 | Done | 10
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-21 | 2024-10-21 | Sprint 4 | Done | 1
PDR Presentation | Aidan, Carly, Diego, John, Matthew, Amber | 2024-09-24 | 2024-10-21 | Sprint 4 | Done | 2
PDR Dry Run | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-21 | 2024-10-21 | Sprint 4 | Done | 1
Preliminary Design Review Presentation | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-08 | 2024-10-22 | Sprint 4 | Done | 5
PDR Slides Review | Carly | 2024-10-18 | 2024-10-22 | Sprint 4 | Done | 5
PDR MVP1 | Carly | 2024-10-14 | 2024-10-22 | Sprint 4 | Done | 3
PDR Key Components | Carly | 2024-10-14 | 2024-10-22 | Sprint 4 | Done | 2
PDR Design Concept | Carly | 2024-10-14 | 2024-10-22 | Sprint 4 | Done | 4
PDR System Block Diagram | Carly | 2024-10-14 | 2024-10-22 | Sprint 4 | Done | 0.25
PDR Key Components and Trade | Carly | 2024-10-17 | 2024-10-22 | Sprint 4 | Done | 1
1st Order Analysis: Cameras Slide PDR | Carly, Amber | 2024-10-15 | 2024-10-22 | Sprint 4 | Done | 0.5
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-28 | 2024-10-28 | Sprint 4 | Done | 1
PDR Team Eval | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-22 | 2024-10-28 | Sprint 4 | Done | 1
Team Evaluation: System Requirements | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-25 | 2024-10-29 | Sprint 4 | Done | 1
Team Evaluation: Preliminary Design Review | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-25 | 2024-10-29 | Sprint 4 | Done | 1
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-04 | 2024-11-04 | Sprint 4 | Done | 1.5
Review broken down dates for PDR to CDR update | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-05 | 2024-11-05 | Sprint 4 | In Progress | 1
[5 empty] | Total Hours | 50.75
24

## Matthew_Sprint_4
Task | Assignees | Start date | End date | Sprint | Status | Hours Completed | Corrective Action
Minimum Viable Product Definition | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-08 | 2024-10-15 | Sprint 4 | Done | 2
Verification Procedures | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-08 | 2024-10-15 | Sprint 4 | Done | 0.5
Drawing/SDD | Matthew, Amber | 2024-10-08 | 2024-10-15 | Sprint 4 | Done | 1.5
PSR4 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-02 | 2024-10-15 | Sprint 4 | Done | 4
Software/firmware for PDR | Matthew, Amber | 2024-10-15 | 2024-10-20 | Sprint 4 | Done | 2
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-21 | 2024-10-21 | Sprint 4 | Done | 1
PDR Presentation | Aidan, Carly, Diego, John, Matthew, Amber | 2024-09-24 | 2024-10-21 | Sprint 4 | Done | 2
PDR Dry Run | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-21 | 2024-10-21 | Sprint 4 | Done | 1
Preliminary Design Review Presentation | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-08 | 2024-10-22 | Sprint 4 | Done | 5
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-28 | 2024-10-28 | Sprint 4 | Done | 1
PDR Team Eval | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-22 | 2024-10-28 | Sprint 4 | Done | 1
Team Evaluation: System Requirements | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-25 | 2024-10-29 | Sprint 4 | Done | 1
Team Evaluation: Preliminary Design Review | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-25 | 2024-10-29 | Sprint 4 | Done | 1
Implement Basic Reverse Projection Algorithm | Matthew | 2024-10-18 | 2024-10-31 | Sprint 4 | Done | 20
Prototype Static Tensor Algorithm Generation | Matthew | 2024-09-24 | 2024-10-31 | Sprint 4 | Done | 40
Prototype and GUI Development | Matthew, Amber | 2024-10-21 | 2024-11-03 | Sprint 4 | Done | 2
Generalize Stitching FrameBuffers for Cameras | Matthew | 2024-10-29 | 2024-11-04 | Sprint 4 | Done | 3
Setup Websocket Connection Framework | Matthew | 2024-11-01 | 2024-11-04 | Sprint 4 | In Progress | 1
Add Static Image Server Routes | Matthew | 2024-10-30 | 2024-11-04 | Sprint 4 | Done | 1
Begin Planning for Client-Server Connection Protocol | Matthew | 2024-10-31 | 2024-11-04 | Sprint 4 | In Progress | 0.5
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-04 | 2024-11-04 | Sprint 4 | Done | 1.5
Review broken down dates for PDR to CDR update | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-05 | 2024-11-05 | Sprint 4 | In Progress | 1
[5 empty] | Total Hours | 93
22

## Aidan_Sprint_4
Task | Assignees | Start date | End date | Sprint | Status | Hours Completed | Corrective Action
Minimum Viable Product Definition | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-08 | 2024-10-15 | Sprint 4 | Done | 2
Verification Procedures | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-08 | 2024-10-15 | Sprint 4 | Done | 0.5
PSR4 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-02 | 2024-10-15 | Sprint 4 | Done | 4
Initial physical configuration for PDR | Aidan, Carly | 2024-10-15 | 2024-10-20 | Sprint 4 | Done | 1
Key components selected for PDR | Aidan, Carly | 2024-10-15 | 2024-10-20 | Sprint 4 | Done | 1
PDR Point Design CAD | Aidan, Carly, John | 2024-10-18 | 2024-10-21 | Sprint 4 | Done | 10
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-21 | 2024-10-21 | Sprint 4 | Done | 1
PDR Presentation | Aidan, Carly, Diego, John, Matthew, Amber | 2024-09-24 | 2024-10-21 | Sprint 4 | Done | 2
PDR Dry Run | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-21 | 2024-10-21 | Sprint 4 | Done | 1
Preliminary Design Review Presentation | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-08 | 2024-10-22 | Sprint 4 | Done | 5
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-28 | 2024-10-28 | Sprint 4 | Done | 1
PDR Team Eval | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-22 | 2024-10-28 | Sprint 4 | Done | 1
Team Evaluation: System Requirements | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-25 | 2024-10-29 | Sprint 4 | Done | 1
Team Evaluation: Preliminary Design Review | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-25 | 2024-10-29 | Sprint 4 | Done | 1
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-04 | 2024-11-04 | Sprint 4 | Done | 1.5
Review broken down dates for PDR to CDR update | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-05 | 2024-11-05 | Sprint 4 | In Progress | 1
[5 empty] | Total Hours | 34
16

## John_Sprint_4
Task | Assignees | Start date | End date | Sprint | Status | Hours Completed | Corrective Action
Minimum Viable Product Definition | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-08 | 2024-10-15 | Sprint 4 | Done | 2
Verification Procedures | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-08 | 2024-10-15 | Sprint 4 | Done | 0.5
PSR4 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-02 | 2024-10-15 | Sprint 4 | Done | 4
MVP SolidWorks Base Assembly | John | 2024-10-20 | 2024-10-21 | Sprint 4 | Done | 5.5
Electrical Schematic PDR | John | 2024-10-20 | 2024-10-21 | Sprint 4 | Done | 1
PDR Point Design CAD | Aidan, Carly, John | 2024-10-18 | 2024-10-21 | Sprint 4 | Done | 10
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-21 | 2024-10-21 | Sprint 4 | Done | 1
PDR Presentation | Aidan, Carly, Diego, John, Matthew, Amber | 2024-09-24 | 2024-10-21 | Sprint 4 | Done | 2
PDR Dry Run | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-21 | 2024-10-21 | Sprint 4 | Done | 1
Preliminary Design Review Presentation | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-08 | 2024-10-22 | Sprint 4 | Done | 5
PDR Slides | John | 2024-10-15 | 2024-10-22 | Sprint 4 | Done | 5.5
Update Electronics Schematic PDR | John | 2024-10-21 | 2024-10-22 | Sprint 4 | Done | 1
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-28 | 2024-10-28 | Sprint 4 | Done | 1
PDR Team Eval | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-22 | 2024-10-28 | Sprint 4 | Done | 1
PDR Personal Run Thru and Review | John | 2024-10-22 | 2024-10-29 | Sprint 4 | Done | 3
Team Evaluation: System Requirements | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-25 | 2024-10-29 | Sprint 4 | Done | 1
Team Evaluation: Preliminary Design Review | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-25 | 2024-10-29 | Sprint 4 | Done | 1
Review and Discuss Action Items | John | 2024-11-04 | 2024-11-04 | Sprint 4 | Done | 0.5
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-04 | 2024-11-04 | Sprint 4 | Done | 1.5
Email ECE Connections for Electrical System Review | John | 2024-11-04 | 2024-11-05 | Sprint 4 | Done | 0.5
Research Batteries | John | 2024-11-04 | 2024-11-05 | Sprint 4 | Done | 0.5
Review broken down dates for PDR to CDR update | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-05 | 2024-11-05 | Sprint 4 | In Progress | 1
[5 empty] | Total Hours | 49.5
22