## Amber_Sprint_9
Task | Assignees | Start date | End date | Sprint | Status | Hours Completed | Corrective Action
Check in status of Camera integration | Matthew, Amber | 2025-01-31 | 2025-01-31 | Sprint 9 | Done | 0.5
Verification Table | Diego, Amber | 2025-02-01 | 2025-02-04 | Sprint 9 | Done | 1
Sponsor Meeting | Aidan, Carly, Diego, John, Matthew, Amber | 2025-02-05 | 2025-02-05 | Sprint 9 | Done | 0.5
Sponsor Meeting | Aidan, Carly, Diego, John, Matthew, Amber | 2025-02-12 | 2025-02-12 | Sprint 9 | Done | 0.5
Design Day Booklet description | Diego, Amber | 2025-02-11 | 2025-02-13 | Sprint 9 | Done | 1.5
[5 empty] | Total Hours | 4 | Total Tasks | 5

## Diego_Sprint_9
Task | Assignees | Start date | End date | Sprint | Status | Hours Completed | Corrective Action
Verification Table | Diego, Amber | 2025-02-01 | 2025-02-04 | Sprint 9 | Done | 1
Sponsor Meeting | Aidan, Carly, Diego, John, Matthew, Amber | 2025-02-05 | 2025-02-05 | Sprint 9 | Done | 0.5
Sponsor Meeting | Aidan, Carly, Diego, John, Matthew, Amber | 2025-02-12 | 2025-02-12 | Sprint 9 | Done | 0.5
Design Day Booklet description | Diego, Amber | 2025-02-11 | 2025-02-13 | Sprint 9 | Done | 1.5
[5 empty] | Total Hours | 3.5 | Total Tasks | 4

## Carly_Sprint_9
Task | Assignees | Start date | End date | Sprint | Status | Hours Completed | Corrective Action
Print 1st Model | Aidan, Carly, John | 2025-02-02 | 2025-02-05 | Sprint 9 | Done | 5
Sponsor Meeting | Aidan, Carly, Diego, John, Matthew, Amber | 2025-02-05 | 2025-02-05 | Sprint 9 | Done | 0.5
ReModel | Aidan, Carly, John | 2025-01-31 | 2025-02-06 | Sprint 9 | Done | 17
Print 2nd Model if needed | Aidan, Carly, John | 2025-02-09 | 2025-02-11 | Sprint 9 | Todo | 3
Sponsor Meeting | Aidan, Carly, Diego, John, Matthew, Amber | 2025-02-12 | 2025-02-12 | Sprint 9 | Done | 0.5
Correct 3D image if needed | Aidan, Carly, John | 2025-02-13 | 2025-02-14 | Sprint 9 | Todo | 4
Correct 3D model if needed 3rd time | Aidan, Carly, John | 2025-02-14 | 2025-02-18 | Sprint 9 | Todo | 4
3rd Redesign | Aidan, Carly, John | 2025-02-18 | 2025-02-18 | Sprint 9 | In Progress | 4
[5 empty] | Total Hours | 38 | Total Tasks | 8

## Matthew_Sprint_9
Task | Assignees | Start date | End date | Sprint | Status | Hours Completed | Corrective Action
Check in status of Camera integration | Matthew, Amber | 2025-01-31 | 2025-01-31 | Sprint 9 | Done | 0.5
Sponsor Meeting | Aidan, Carly, Diego, John, Matthew, Amber | 2025-02-05 | 2025-02-05 | Sprint 9 | Done | 0.5
Integrate Object detection | Matthew | 2025-02-03 | 2025-02-09 | Sprint 9 | In Progress | 15
Sponsor Meeting | Aidan, Carly, Diego, John, Matthew, Amber | 2025-02-12 | 2025-02-12 | Sprint 9 | Done | 0.5
Debug Argus | Matthew | 2025-02-11 | 2025-02-18 | Sprint 9 | In Progress | 30
[5 empty] | Total Hours | 46.5 | Total Tasks | 5

## Aidan_Sprint_9
Task | Assignees | Start date | End date | Sprint | Status | Hours Completed | Corrective Action
Print 1st Model | Aidan, Carly, John | 2025-02-02 | 2025-02-05 | Sprint 9 | Done | 5
Sponsor Meeting | Aidan, Carly, Diego, John, Matthew, Amber | 2025-02-05 | 2025-02-05 | Sprint 9 | Done | 0.5
ReModel | Aidan, Carly, John | 2025-01-31 | 2025-02-06 | Sprint 9 | Done | 17
Print 2nd Model if needed | Aidan, Carly, John | 2025-02-09 | 2025-02-11 | Sprint 9 | Todo | 3
Sponsor Meeting | Aidan, Carly, Diego, John, Matthew, Amber | 2025-02-12 | 2025-02-12 | Sprint 9 | Done | 0.5
Correct 3D image if needed | Aidan, Carly, John | 2025-02-13 | 2025-02-14 | Sprint 9 | Todo | 4
Correct 3D model if needed 3rd time | Aidan, Carly, John | 2025-02-14 | 2025-02-18 | Sprint 9 | Todo | 4
3rd Redesign | Aidan, Carly, John | 2025-02-18 | 2025-02-18 | Sprint 9 | In Progress | 4
[5 empty] | Total Hours | 38 | Total Tasks | 8

## John_Sprint_9
Task | Assignees | Start date | End date | Sprint | Status | Hours Completed | Corrective Action
Print 1st Model | Aidan, Carly, John | 2025-02-02 | 2025-02-05 | Sprint 9 | Done | 5
Sponsor Meeting | Aidan, Carly, Diego, John, Matthew, Amber | 2025-02-05 | 2025-02-05 | Sprint 9 | Done | 0.5
ReModel | Aidan, Carly, John | 2025-01-31 | 2025-02-06 | Sprint 9 | Done | 17
Print 2nd Model if needed | Aidan, Carly, John | 2025-02-09 | 2025-02-11 | Sprint 9 | Todo | 3
Sponsor Meeting | Aidan, Carly, Diego, John, Matthew, Amber | 2025-02-12 | 2025-02-12 | Sprint 9 | Done | 0.5
Correct 3D image if needed | Aidan, Carly, John | 2025-02-13 | 2025-02-14 | Sprint 9 | Todo | 4
Correct 3D model if needed 3rd time | Aidan, Carly, John | 2025-02-14 | 2025-02-18 | Sprint 9 | Todo | 4
3rd Redesign | Aidan, Carly, John | 2025-02-18 | 2025-02-18 | Sprint 9 | In Progress | 4
[5 empty] | Total Hours | 38 | Total Tasks | 8

## Team Summary
Team Member | Task | Hours
Amber | 4 | 15
John | 8 | 38
Carly | 8 | 38
Aidan | 8 | 38
Matthew | 5 | 46
Diego | 4 | 17