## Amber_Sprint_8
Task | Assignees | Start date | End date | Sprint | Status | Hours Completed | Corrective Action
SDD review before changes | Matthew, Amber | 2025-01-17 | 2025-01-19 | Sprint 8 | Done | 1
TDP1 Document | Aidan, Carly, Diego, John, Matthew, Amber | 2025-01-13 | 2025-01-22 | Sprint 8 | Done | 6
Redo SDD | Amber | 2025-01-21 | 2025-01-24 | Sprint 8 | Done | 7
SDD requirments | Amber | 2025-01-20 | 2025-01-24 | Sprint 8 | Done | 3
TDP Document Review | Amber | 2025-01-19 | 2025-01-25 | Sprint 8 | Done | 3
Test Plan | Amber | 2025-01-22 | 2025-01-25 | Sprint 8 | Done | 3
Object detection implementation | Matthew, Amber | 2025-01-22 | 2025-01-25 | Sprint 8 | In Progress | 10
Test Verification update/redo | Amber | 2025-01-22 | 2025-01-26 | Sprint 8 | Done | 2
Graphic and better metric test | Amber | 2025-01-27 | 2025-01-28 | Sprint 8 | Done | 2
ISR2 Slides | Aidan, Carly, Diego, John, Matthew, Amber | 2025-02-15 | 2025-02-25 | Sprint 8 | Todo
[5 empty] | Total Hours | 37
| Tasks | Hours
Amber | 10 | 37
Diego | 2 | 6
Carly | 6 | 37
Matthew | 8 | 36
Aidan | 5 | 33
John | 5 | 36

## Diego_Sprint_8
Task | Assignees | Start date | End date | Sprint | Status | Hours Completed | Corrective Action
TDP1 Document | Aidan, Carly, Diego, John, Matthew, Amber | 2025-01-13 | 2025-01-22 | Sprint 8 | Done | 6
ISR2 Slides | Aidan, Carly, Diego, John, Matthew, Amber | 2025-02-15 | 2025-02-25 | Sprint 8 | Todo
[5 empty] | Total Hours | 6

## Carly_Sprint_8
Task | Assignees | Start date | End date | Sprint | Status | Hours Completed | Corrective Action
Plane 3d Print One | Aidan, Carly | 2025-01-17 | 2025-01-19 | Sprint 8 | Done
TDP1 Document | Aidan, Carly, Diego, John, Matthew, Amber | 2025-01-13 | 2025-01-22 | Sprint 8 | Done | 6
Plane Re-Design (Carly) | Carly | 2025-01-24 | 2025-01-26 | Sprint 8 | Done | 26
Indentured Drawing List Update | Carly | 2025-01-16 | 2025-01-28 | Sprint 8 | Done | 1
CASA Drawings (Carly) | Carly | 2025-01-26 | 2025-01-28 | Sprint 8 | Done | 4
ISR2 Slides | Aidan, Carly, Diego, John, Matthew, Amber | 2025-02-15 | 2025-02-25 | Sprint 8 | Todo
[5 empty] | Total Hours | 37

## Matthew_Sprint_8
Task | Assignees | Start date | End date | Sprint | Status | Hours Completed | Corrective Action
SDD review before changes | Matthew, Amber | 2025-01-17 | 2025-01-19 | Sprint 8 | Done | 1
Fit 3d print with system | Matthew | 2025-01-20 | 2025-01-20 | Sprint 8 | Done | 1
TDP1 Document | Aidan, Carly, Diego, John, Matthew, Amber | 2025-01-13 | 2025-01-22 | Sprint 8 | Done | 6
Object detection implementation | Matthew, Amber | 2025-01-22 | 2025-01-25 | Sprint 8 | In Progress | 10
Create Argus bindings | Matthew | 2025-01-29 | 2025-01-31 | Sprint 8 | In Progress | 6
Integrate new cameras into software | Matthew | 2025-01-24 | 2025-02-06 | Sprint 8 | In Progress | 10
Improve software error handling recovery | Matthew | 2025-01-17 | 2025-02-06 | Sprint 8 | In Progress | 2
ISR2 Slides | Aidan, Carly, Diego, John, Matthew, Amber | 2025-02-15 | 2025-02-25 | Sprint 8 | Todo
[5 empty] | Total Hours | 36

## Aidan_Sprint_8
Task | Assignees | Start date | End date | Sprint | Status | Hours Completed | Corrective Action
Plane 3d Print One | Aidan, Carly | 2025-01-17 | 2025-01-19 | Sprint 8 | Done
TDP1 Document | Aidan, Carly, Diego, John, Matthew, Amber | 2025-01-13 | 2025-01-22 | Sprint 8 | Done | 6
Plane Re-Design (Aidan) | Aidan | 2025-01-24 | 2025-01-26 | Sprint 8 | Done | 26
Exploded CASA Drawing (Aidan) | Aidan | 2025-01-26 | 2025-01-28 | Sprint 8 | Done | 1
ISR2 Slides | Aidan, Carly, Diego, John, Matthew, Amber | 2025-02-15 | 2025-02-25 | Sprint 8 | Todo
[5 empty] | Total Hours | 33

## John_Sprint_8
Task | Assignees | Start date | End date | Sprint | Status | Hours Completed | Corrective Action
TDP1 Document | Aidan, Carly, Diego, John, Matthew, Amber | 2025-01-13 | 2025-01-22 | Sprint 8 | Done | 6
Plane Re-Design (John) | John | 2025-01-24 | 2025-01-26 | Sprint 8 | Done | 26
Diorama Ground Vehicles Revisions & Drawings (John) | John | 2025-01-26 | 2025-01-28 | Sprint 8 | Done | 2
MVP Drawings (John) | John | 2025-01-26 | 2025-01-28 | Sprint 8 | Done | 2
ISR2 Slides | Aidan, Carly, Diego, John, Matthew, Amber | 2025-02-15 | 2025-02-25 | Sprint 8 | Todo
[5 empty] | Total Hours | 36