## Sprint Sprint 1
Task | Assignees | Start date | End date | Sprint | Status | Hours Completed | Corrective Action
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-09-02 | 2024-09-02 | Sprint 1 | Done | 1
[5 empty] | Total Hours | 1
1

## Sprint Sprint 2
Task | Assignees | Start date | End date | Sprint | Status | Hours Completed | Corrective Action
Sponsor meeting @3:30 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-09-04 | 2024-09-04 | Sprint 2 | Done | 0.5
Conduct Reseach on Project options | Aidan, Carly, Diego, John, Matthew, Amber | 2024-09-06 | 2024-09-09 | Sprint 2 | Done | 2
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-09-09 | 2024-09-09 | Sprint 2 | Done | 1
Team Charter | John, Amber | 2024-09-06 | 2024-09-09 | Sprint 2 | Done | 3
Email sponsor ConOps and questions for review | Amber | 2024-09-09 | 2024-09-10 | Sprint 2 | Done | 0.25
ConOps | Diego, Amber | 2024-09-05 | 2024-09-11 | Sprint 2 | Done | 5
Sponsor meeting @3:30 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-09-11 | 2024-09-11 | Sprint 2 | Done | 0.5
Add questions for Jake and Deigo in drive | Aidan, Carly, Diego, John, Matthew, Amber | 2024-09-09 | 2024-09-11 | Sprint 2 | Done | 1
Email professor about sponsor PDR date request for 10/29 to go first | Amber | 2024-09-11 | 2024-09-12 | Sprint 2 | Done | 0.25
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-09-16 | 2024-09-16 | Sprint 2 | Done | 1
Functional Requirements & Functional Block Diagram | Aidan, Diego, Amber | 2024-09-12 | 2024-09-16 | Sprint 2 | Done | 3
PSR2 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-09-06 | 2024-09-17 | Sprint 2 | Done | 2
Sponsor Meeting 3 Questions 9/18/2024 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-09-16 | 2024-09-17 | Sprint 2 | Done | 0.5
Sponsor meeting @3:30 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-09-18 | 2024-09-18 | Sprint 2 | Done | 0.5
Camera angle placement drawing | Carly, John | 2024-09-19 | 2024-09-19 | Sprint 2 | Done | 1
Trades & Point Design | Aidan, Carly, Diego, John, Matthew, Amber | 2024-09-13 | 2024-09-19 | Sprint 2 | Done | 2
Email Jake and Diego about Proposal draft | Amber | 2024-09-20 | 2024-09-20 | Sprint 2 | Done | 0.25
figure out scrimmage dates | Aidan | 2024-09-16 | 2024-09-20 | Sprint 2 | Done | 0.25
Subcontractors and consultants | Matthew | 2024-09-16 | 2024-09-21 | Sprint 2 | Done | 0.25
Customer Furnished Equipment | Aidan | 2024-09-16 | 2024-09-21 | Sprint 2 | Done | 0.5
Facilities/ Equipment in proposal | Aidan | 2024-09-16 | 2024-09-21 | Sprint 2 | Done | 0.5
Statement of Work in Proposal | Amber | 2024-09-16 | 2024-09-21 | Sprint 2 | Done | 0.5
Signatures and resumes in Proposal | Aidan, Carly, Diego, John, Matthew, Amber | 2024-09-16 | 2024-09-21 | Sprint 2 | Done | 0.5
Related Work- in proposal | John | 2024-09-16 | 2024-09-21 | Sprint 2 | Done | 1
Key personal- in Proposal | Carly | 2024-09-16 | 2024-09-21 | Sprint 2 | Done | 0.5
Data Restriction | Carly | 2024-09-16 | 2024-09-21 | Sprint 2 | Done | 0.25
Functional Block Diagram , functional requirements in proposal | Diego, Amber | 2024-09-16 | 2024-09-22 | Sprint 2 | Done | 3
Set up Reoccurring zoom meeting link with sponsors | Amber | 2024-09-23 | 2024-09-23 | Sprint 2 | Done | 0.25
Turn in Proposal | Carly, John, Matthew, Amber | 2024-09-16 | 2024-09-23 | Sprint 2 | Done | 0.25
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-09-23 | 2024-09-23 | Sprint 2 | Done | 1
Team Evaluation:Proposal | Aidan, Carly, Diego, John, Matthew, Amber | 2024-09-20 | 2024-09-24 | Sprint 2 | Done | 1.75
Get signatures from Sponsors for Proposal | Amber | 2024-09-23 | 2024-09-24 | Sprint 2 | Done | 0.5
Get Jim's Signature for Proposal | Amber | 2024-09-23 | 2024-09-24 | Sprint 2 | Done | 0.25
SBD | Carly | 2024-09-19 | 2024-09-26 | Sprint 2 | Done | 2.5
Assign everyone to a part of the Systems Requirement Document | Amber | 2024-09-27 | 2024-09-29 | Sprint 2 | Done | 0.5
Schedule a dry run for PDR | Amber | 2024-09-30 | 2024-09-30 | Sprint 2 | Done
Break up work for PDR and CDR | Amber | 2024-09-30 | 2024-09-30 | Sprint 2 | Done | 1
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-09-30 | 2024-09-30 | Sprint 2 | Done | 1
[5 empty] | Total Hours | 40
38

## Sprint Sprint 3
Task | Assignees | Start date | End date | Sprint | Status | Hours Completed | Corrective Action
System Requirements Verification Matrix | Diego | 2024-09-26 | 2024-10-01 | Sprint 3 | Done | 1
PSR3 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-09-19 | 2024-10-01 | Sprint 3 | Done | 1.5
Camera Equation for prototyping plan | Matthew | 2024-09-30 | 2024-10-03 | Sprint 3 | Done | 0.25
Camera Research | Carly | 2024-10-03 | 2024-10-03 | Sprint 3 | Done | 1.5
Requirements Scrimmage slides setup | John | 2024-10-03 | 2024-10-03 | Sprint 3 | Done | 1
Requirements Scrimmage 1 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-09-12 | 2024-10-03 | Sprint 3 | Done | 2.5
Power Equation for Prototyping Plan | Carly, John | 2024-09-30 | 2024-10-03 | Sprint 3 | Done | 0.5
Research Project Fundamentals, modeling & Prototype Plan | Aidan, Carly, Diego, John, Matthew, Amber | 2024-09-23 | 2024-10-03 | Sprint 3 | Done | 1.5
Yolo equation for prototyping plan | Amber | 2024-09-30 | 2024-10-03 | Sprint 3 | Done | 0.25
verification matrix for SRD | Carly, Diego | 2024-09-30 | 2024-10-04 | Sprint 3 | Done | 1
Send requirements matrix to Jake and Diego | Amber | 2024-09-30 | 2024-10-04 | Sprint 3 | Done | 0.25
SRD- Reference spec sheet for cameras | Matthew | 2024-09-30 | 2024-10-04 | Sprint 3 | Done | 0.5
SRD-Standards and help out with referenced documents | Matthew | 2024-09-30 | 2024-10-04 | Sprint 3 | Done | 1
Reference for SRD | John | 2024-09-30 | 2024-10-04 | Sprint 3 | Done | 0.5
SRD-requirements verification | Carly | 2024-09-30 | 2024-10-04 | Sprint 3 | Done | 1
Email Jake and Diego about scheduling a tour | Amber | 2024-10-02 | 2024-10-04 | Sprint 3 | Done | 0.25
SRD-Definitions, acronyms, and abbreviations | Aidan | 2024-09-30 | 2024-10-04 | Sprint 3 | Done | 1
All requirements by system for SRD | Diego, Amber | 2024-09-30 | 2024-10-04 | Sprint 3 | Done | 1.5
Email Jake and Diego PDR information | Amber | 2024-10-02 | 2024-10-06 | Sprint 3 | Done | 0.25
System Requirements Document:5.0-Verification Requirements | Aidan, Carly, Diego, John, Matthew, Amber | 2024-09-27 | 2024-10-07 | Sprint 3 | Done | 0.5
System Requirements Document: 4.0-Requirements | Aidan, Carly, Diego, John, Matthew, Amber | 2024-09-27 | 2024-10-07 | Sprint 3 | Done | 1
System Requirements Document:8.0-Ability to formulate a design problem for specified needs and technical requirements (O2a) | Aidan, Carly, Diego, John, Matthew, Amber | 2024-09-27 | 2024-10-07 | Sprint 3 | Done | 0.5
System Requirements Document:6.0-System Requirements Verification Matrix (SRVM) | Aidan, Carly, Diego, John, Matthew, Amber | 2024-09-27 | 2024-10-07 | Sprint 3 | Done | 1
Importance and Significance for scrimmage slides | John | 2024-10-03 | 2024-10-07 | Sprint 3 | Done | 1
System Requirements Document: 3.0-Definitions, Acronyms and Abbreviations | Aidan, Carly, Diego, John, Matthew, Amber | 2024-09-27 | 2024-10-07 | Sprint 3 | Done | 0.25
System Requirements Document: 1.0-Introduction and Scope (Background, Need, ConOps, Stakeholders) | Aidan, Carly, Diego, John, Matthew, Amber | 2024-09-27 | 2024-10-07 | Sprint 3 | Done | 1.5
System Requirements Document:2.0-Applicable Documents (references in SRD including Standards) | Aidan, Carly, Diego, John, Matthew, Amber | 2024-09-27 | 2024-10-07 | Sprint 3 | Done | 1
Summary for scrimmage slides | Diego | 2024-10-03 | 2024-10-07 | Sprint 3 | Done | 1
Background for scrimmage slides | Aidan | 2024-10-03 | 2024-10-07 | Sprint 3 | Done
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-07 | 2024-10-07 | Sprint 3 | Done | 1
System Requirements Document:7.0-Notes | Aidan, Carly, Diego, John, Matthew, Amber | 2024-09-27 | 2024-10-07 | Sprint 3 | Done | 0.5
Requirements Flow Down | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-01 | 2024-10-08 | Sprint 3 | Done | 2
scope for SRD | Amber | 2024-09-30 | 2024-10-08 | Sprint 3 | Done | 0.25
Team Evaluation: System Requirements | Aidan, Carly, Diego, John, Matthew, Amber | 2024-09-27 | 2024-10-10 | Sprint 3 | Done | 0.5
System Requirements Document | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-01 | 2024-10-10 | Sprint 3 | Done | 2
Edit Code for PDR to include individual tasks for each team member with hours | Amber | 2024-10-01 | 2024-10-11 | Sprint 3 | Done | 1
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-14 | 2024-10-14 | Sprint 3 | Done | 1
UX for GUI | Amber | 2024-10-14 | 2024-10-22 | Sprint 3 | Done | 1.5
[5 empty] | Total Hours | 34.75

## Sprint Sprint 4
Task | Assignees | Start date | End date | Sprint | Status | Hours Completed | Corrective Action
Requirements for slides | Amber | 2024-10-03 | 2024-10-07 | Sprint 4 | Done | 0.5
PSR4 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-02 | 2024-10-15 | Sprint 4 | Done | 4
Drawing/SDD | Matthew, Amber | 2024-10-08 | 2024-10-15 | Sprint 4 | Done | 1.5
Minimum Viable Product Definition | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-08 | 2024-10-15 | Sprint 4 | Done | 2
Verification Procedures | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-08 | 2024-10-15 | Sprint 4 | Done | 0.5
GUI UI for PDR | Amber | 2024-10-15 | 2024-10-18 | Sprint 4 | Done | 0.5
MVP CAD drawings for PDR | Carly | 2024-10-15 | 2024-10-18 | Sprint 4 | Done | 1
Risk/Mitigation for PDR | Amber | 2024-10-15 | 2024-10-20 | Sprint 4 | Done | 1
Software/firmware for PDR | Matthew, Amber | 2024-10-15 | 2024-10-20 | Sprint 4 | Done | 2
Initial physical configuration for PDR | Aidan, Carly | 2024-10-15 | 2024-10-20 | Sprint 4 | Done | 1
Project Plan, Status, Deliverables, & Budget Analysis for PDR | Diego, Amber | 2024-10-15 | 2024-10-20 | Sprint 4 | Done | 1
Key components selected for PDR | Aidan, Carly | 2024-10-15 | 2024-10-20 | Sprint 4 | Done | 1
PDR Dry Run | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-21 | 2024-10-21 | Sprint 4 | Done | 1
Electrical Schematic PDR | John | 2024-10-20 | 2024-10-21 | Sprint 4 | Done | 1
MVP SolidWorks Base Assembly | John | 2024-10-20 | 2024-10-21 | Sprint 4 | Done | 5.5
PDR Presentation | Aidan, Carly, Diego, John, Matthew, Amber | 2024-09-24 | 2024-10-21 | Sprint 4 | Done | 2
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-21 | 2024-10-21 | Sprint 4 | Done | 1
PDR Point Design CAD | Aidan, Carly, John | 2024-10-18 | 2024-10-21 | Sprint 4 | Done | 10
Update Electronics Schematic PDR | John | 2024-10-21 | 2024-10-22 | Sprint 4 | Done | 1
PDR Key Components and Trade | Carly | 2024-10-17 | 2024-10-22 | Sprint 4 | Done | 1
PDR Slides | John | 2024-10-15 | 2024-10-22 | Sprint 4 | Done | 5.5
PDR Slides Review | Carly | 2024-10-18 | 2024-10-22 | Sprint 4 | Done | 5
PDR MVP1 | Carly | 2024-10-14 | 2024-10-22 | Sprint 4 | Done | 3
PDR Key Components | Carly | 2024-10-14 | 2024-10-22 | Sprint 4 | Done | 2
PDR Design Concept | Carly | 2024-10-14 | 2024-10-22 | Sprint 4 | Done | 4
PDR System Block Diagram | Carly | 2024-10-14 | 2024-10-22 | Sprint 4 | Done | 0.25
Preliminary Design Review Presentation | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-08 | 2024-10-22 | Sprint 4 | Done | 5
Risk/Mitigation | Amber | 2024-10-15 | 2024-10-22 | Sprint 4 | Done | 1
Requirements Slide PDR | Amber | 2024-10-14 | 2024-10-22 | Sprint 4 | Done | 0.5
Communication TPD Slide PDR | Amber | 2024-10-15 | 2024-10-22 | Sprint 4 | Done | 0.5
Project Deliverable Slide | Amber | 2024-10-15 | 2024-10-22 | Sprint 4 | Done | 1
PDR Summary Slide | Amber | 2024-10-15 | 2024-10-22 | Sprint 4 | Done | 0.5
1st Order Analysis: Cameras Slide PDR | Carly, Amber | 2024-10-15 | 2024-10-22 | Sprint 4 | Done | 0.5
Project Plan to CDR Slide | Amber | 2024-10-15 | 2024-10-22 | Sprint 4 | Done | 1
PDR Team Eval | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-22 | 2024-10-28 | Sprint 4 | Done | 1
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-28 | 2024-10-28 | Sprint 4 | Done | 1
PDR Personal Run Thru and Review | John | 2024-10-22 | 2024-10-29 | Sprint 4 | Done | 3
Team Evaluation: Preliminary Design Review | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-25 | 2024-10-29 | Sprint 4 | Done | 1
Team Evaluation: System Requirements | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-25 | 2024-10-29 | Sprint 4 | Done | 1
Implement Basic Reverse Projection Algorithm | Matthew | 2024-10-18 | 2024-10-31 | Sprint 4 | Done | 20
Prototype Static Tensor Algorithm Generation | Matthew | 2024-09-24 | 2024-10-31 | Sprint 4 | Done | 40
Prototype and GUI Development | Matthew, Amber | 2024-10-21 | 2024-11-03 | Sprint 4 | Done | 2
Review and Discuss Action Items | John | 2024-11-04 | 2024-11-04 | Sprint 4 | Done | 0.5
Setup Websocket Connection Framework | Matthew | 2024-11-01 | 2024-11-04 | Sprint 4 | Done | 1
Begin Planning for Client-Server Connection Protocol | Matthew | 2024-10-31 | 2024-11-04 | Sprint 4 | Done | 0.5
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-04 | 2024-11-04 | Sprint 4 | Done | 1.5
Generalize Stitching FrameBuffers for Cameras | Matthew | 2024-10-29 | 2024-11-04 | Sprint 4 | Done | 3
Add Static Image Server Routes | Matthew | 2024-10-30 | 2024-11-04 | Sprint 4 | Done | 1
Research Batteries | John | 2024-11-04 | 2024-11-05 | Sprint 4 | Done | 0.5
Email ECE Connections for Electrical System Review | John | 2024-11-04 | 2024-11-05 | Sprint 4 | Done | 0.5
Review broken down dates for PDR to CDR update | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-05 | 2024-11-05 | Sprint 4 | Done | 1
Scope for PDR | Amber | 2024-10-14 | 2024-11-22 | Sprint 4 | Done | 0.25
[5 empty] | Total Hours | 147

## Sprint Sprint 6
Task | Assignees | Start date | End date | Sprint | Status | Hours Completed | Corrective Action
Practice CDR | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-25 | 2024-10-28 | Sprint 6 | Todo
PSR6 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-06 | 2024-11-21 | Sprint 6 | Todo
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-25 | 2024-11-25 | Sprint 6 | Todo
Finalize Prototype | Matthew, Amber | 2024-11-21 | 2024-11-25 | Sprint 6 | Todo
CDR Email Sponsor to Review | Amber | 2024-11-29 | 2024-11-29 | Sprint 6 | Todo
Revise CDR | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-25 | 2024-11-29 | Sprint 6 | Todo
Test Prototype | Matthew, Amber | 2024-11-22 | 2024-11-30 | Sprint 6 | Todo
Add bounding box capability to Transmission Protocol | Matthew, Amber | 2024-11-22 | 2024-11-30 | Sprint 6 | Todo
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-12-02 | 2024-12-02 | Sprint 6 | Todo
Critical Design Review Presentation | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-19 | 2024-12-03 | Sprint 6 | Todo
CDR/ISR Presentation | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-05 | 2024-12-03 | Sprint 6 | Todo
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-12-09 | 2024-12-09 | Sprint 6 | Todo
Team Evaluation: Critical Design Review | Aidan, Carly, Diego, John, Matthew, Amber | 2024-12-06 | 2024-12-10 | Sprint 6 | Todo
CDR/ISR Team Eval | Aidan, Carly, Diego, John, Matthew, Amber | 2024-12-05 | 2024-12-10 | Sprint 6 | Todo
[5 empty] | Total Hours | 0

## Sprint Sprint 5
Task | Assignees | Start date | End date | Sprint | Status | Hours Completed | Corrective Action
PSR5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-16 | 2024-11-05 | Sprint 5 | Done | 2
Fix Framebuffer Update Regression | Matthew | 2024-11-04 | 2024-11-06 | Sprint 5 | Done | 3
Primitive Live Loading Capability | Matthew, Amber | 2024-11-04 | 2024-11-08 | Sprint 5 | Done | 4
Have GUI prototype | Amber | 2024-11-04 | 2024-11-10 | Sprint 5 | In Progress | 4
Basic Server Video Transmission | Matthew | 2024-11-04 | 2024-11-10 | Sprint 5 | In Progress | 6
Basic UI Video Transmission | Amber | 2024-11-04 | 2024-11-10 | Sprint 5 | Done | 2
Determine Transmission Protocol Definition | Matthew | 2024-11-08 | 2024-11-10 | Sprint 5 | In Progress | 2
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-11 | 2024-11-11 | Sprint 5 | Done | 1.5
Refine Live Loading Implementation | Matthew | 2024-11-06 | 2024-11-12 | Sprint 5 | Done | 15
Parker Meggit Tour | Aidan, Diego, Matthew, Amber | 2024-11-12 | 2024-11-12 | Sprint 5 | Done | 1
Add UI controls | Amber | 2024-11-06 | 2024-11-14 | Sprint 5 | In Progress | 2
Determine Controls API Definition | Matthew, Amber | 2024-11-06 | 2024-11-14 | Sprint 5 | Done | 1
Testing Prototype | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-31 | 2024-11-15 | Sprint 5 | In Progress | 2
Diorama Design | Carly, John | 2024-11-05 | 2024-11-15 | Sprint 5 | In Progress | 4
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-18 | 2024-11-18 | Sprint 5 | Done | 1
Update Risks | Amber | 2024-11-18 | 2024-11-22 | Sprint 5 | In Progress | 1
Update slides CDR Slides | Diego, Amber | 2024-11-18 | 2024-11-22 | Sprint 5 | In Progress | 5
Add Server Endpoints for controls | Matthew | 2024-11-06 | 2024-11-22 | Sprint 5 | In Progress | 5
MVP2 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-18 | 2024-11-22 | Sprint 5 | In Progress
Transfer slides from PDR to CDR | Diego, Amber | 2024-11-18 | 2024-11-22 | Sprint 5 | In Progress | 5
MVP2 CAD Design | Aidan, Carly, John | 2024-11-18 | 2024-11-22 | Sprint 5 | In Progress
CDR Drawings | Aidan, Carly, John | 2024-11-05 | 2024-11-25 | Sprint 5 | In Progress
CAD Diorama pieces | John | 2024-11-18 | 2024-11-25 | Sprint 5 | In Progress | 10
CAD Plane | Aidan | 2024-11-18 | 2024-11-25 | Sprint 5 | In Progress | 10
CAD- Mounting brackets for all electronics | Carly | 2024-11-15 | 2024-11-25 | Sprint 5 | In Progress | 10
Diorama Manufacturing | Carly, John | 2024-11-15 | 2024-11-25 | Sprint 5 | In Progress
Switch to GPU Projection | Matthew | 2024-11-11 | 2024-11-25 | Sprint 5 | In Progress
Add Video Compression to server and client, if necessary | Matthew, Amber | 2024-11-22 | 2024-11-30 | Sprint 5 | Todo
[5 empty] | Total Hours | 96.5

## Sheet1
| ToDo | In Progress | Done
Sprint 1 | 1 | 0 | 1
Sprint 2 |  |  | 38
Sprint 3 |  |  | 38
Sprint 4 |  |  | 52
Sprint 5 | 1 | 18 | 9