## Amber_Sprint_5
Task | Assignees | Start date | End date | Sprint | Status | Hours Completed | Corrective Action
PSR5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-16 | 2024-11-05 | Sprint 5 | Done | 2
Primitive Live Loading Capability | Matthew, Amber | 2024-11-04 | 2024-11-08 | Sprint 5 | Done | 4
Have GUI prototype | Amber | 2024-11-04 | 2024-11-10 | Sprint 5 | In Progress | 4
Basic UI Video Transmission | Amber | 2024-11-04 | 2024-11-10 | Sprint 5 | Done | 2
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-11 | 2024-11-11 | Sprint 5 | Done | 1.5
Parker Meggit Tour | Aidan, Diego, Matthew, Amber | 2024-11-12 | 2024-11-12 | Sprint 5 | Done | 1
Add UI controls | Amber | 2024-11-06 | 2024-11-14 | Sprint 5 | In Progress | 2
Determine Controls API Definition | Matthew, Amber | 2024-11-06 | 2024-11-14 | Sprint 5 | Done | 1
Testing Prototype | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-31 | 2024-11-15 | Sprint 5 | In Progress | 2
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-18 | 2024-11-18 | Sprint 5 | Done | 1
Update Risks | Amber | 2024-11-18 | 2024-11-22 | Sprint 5 | In Progress | 1
Update slides CDR Slides | Diego, Amber | 2024-11-18 | 2024-11-22 | Sprint 5 | In Progress | 5
MVP2 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-18 | 2024-11-22 | Sprint 5 | In Progress
Transfer slides from PDR to CDR | Diego, Amber | 2024-11-18 | 2024-11-22 | Sprint 5 | In Progress | 5
Add Video Compression to server and client, if necessary | Matthew, Amber | 2024-11-22 | 2024-11-30 | Sprint 5 | Todo
[5 empty] | Total Hours | 31.5
15

## Diego_Sprint_5
Task | Assignees | Start date | End date | Sprint | Status | Hours Completed | Corrective Action
PSR5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-16 | 2024-11-05 | Sprint 5 | Done | 2
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-11 | 2024-11-11 | Sprint 5 | Done | 1.5
Parker Meggit Tour | Aidan, Diego, Matthew, Amber | 2024-11-12 | 2024-11-12 | Sprint 5 | Done | 1
Testing Prototype | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-31 | 2024-11-15 | Sprint 5 | In Progress | 2
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-18 | 2024-11-18 | Sprint 5 | Done | 1
Update slides CDR Slides | Diego, Amber | 2024-11-18 | 2024-11-22 | Sprint 5 | In Progress | 5
MVP2 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-18 | 2024-11-22 | Sprint 5 | In Progress
Transfer slides from PDR to CDR | Diego, Amber | 2024-11-18 | 2024-11-22 | Sprint 5 | In Progress | 5
[5 empty] | Total Hours | 17.5
8

## Carly_Sprint_5
Task | Assignees | Start date | End date | Sprint | Status | Hours Completed | Corrective Action
PSR5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-16 | 2024-11-05 | Sprint 5 | Done | 2
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-11 | 2024-11-11 | Sprint 5 | Done | 1.5
Testing Prototype | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-31 | 2024-11-15 | Sprint 5 | In Progress | 2
Diorama Design | Carly, John | 2024-11-05 | 2024-11-15 | Sprint 5 | In Progress | 4
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-18 | 2024-11-18 | Sprint 5 | Done | 1
MVP2 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-18 | 2024-11-22 | Sprint 5 | In Progress
MVP2 CAD Design | Aidan, Carly, John | 2024-11-18 | 2024-11-22 | Sprint 5 | In Progress
CDR Drawings | Aidan, Carly, John | 2024-11-05 | 2024-11-25 | Sprint 5 | In Progress
CAD- Mounting brackets for all electronics | Carly | 2024-11-15 | 2024-11-25 | Sprint 5 | In Progress | 10
Diorama Manufacturing | Carly, John | 2024-11-15 | 2024-11-25 | Sprint 5 | In Progress
[5 empty] | Total Hours | 20.5
10

## Matthew_Sprint_5
Task | Assignees | Start date | End date | Sprint | Status | Hours Completed | Corrective Action
PSR5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-16 | 2024-11-05 | Sprint 5 | Done | 2
Fix Framebuffer Update Regression | Matthew | 2024-11-04 | 2024-11-06 | Sprint 5 | Done | 3
Primitive Live Loading Capability | Matthew, Amber | 2024-11-04 | 2024-11-08 | Sprint 5 | Done | 4
Basic Server Video Transmission | Matthew | 2024-11-04 | 2024-11-10 | Sprint 5 | In Progress | 6
Determine Transmission Protocol Definition | Matthew | 2024-11-08 | 2024-11-10 | Sprint 5 | In Progress | 2
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-11 | 2024-11-11 | Sprint 5 | Done | 1.5
Refine Live Loading Implementation | Matthew | 2024-11-06 | 2024-11-12 | Sprint 5 | Done | 15
Parker Meggit Tour | Aidan, Diego, Matthew, Amber | 2024-11-12 | 2024-11-12 | Sprint 5 | Done | 1
Determine Controls API Definition | Matthew, Amber | 2024-11-06 | 2024-11-14 | Sprint 5 | Done | 1
Testing Prototype | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-31 | 2024-11-15 | Sprint 5 | In Progress | 2
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-18 | 2024-11-18 | Sprint 5 | Done | 1
Add Server Endpoints for controls | Matthew | 2024-11-06 | 2024-11-22 | Sprint 5 | In Progress | 5
MVP2 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-18 | 2024-11-22 | Sprint 5 | In Progress
Switch to GPU Projection | Matthew | 2024-11-11 | 2024-11-25 | Sprint 5 | In Progress
Add Video Compression to server and client, if necessary | Matthew, Amber | 2024-11-22 | 2024-11-30 | Sprint 5 | Todo
[5 empty] | Total Hours | 43.5
15

## Aidan_Sprint_5
Task | Assignees | Start date | End date | Sprint | Status | Hours Completed | Corrective Action
PSR5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-16 | 2024-11-05 | Sprint 5 | Done | 2
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-11 | 2024-11-11 | Sprint 5 | Done | 1.5
Parker Meggit Tour | Aidan, Diego, Matthew, Amber | 2024-11-12 | 2024-11-12 | Sprint 5 | Done | 1
Testing Prototype | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-31 | 2024-11-15 | Sprint 5 | In Progress | 2
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-18 | 2024-11-18 | Sprint 5 | Done | 1
MVP2 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-18 | 2024-11-22 | Sprint 5 | In Progress
MVP2 CAD Design | Aidan, Carly, John | 2024-11-18 | 2024-11-22 | Sprint 5 | In Progress
CDR Drawings | Aidan, Carly, John | 2024-11-05 | 2024-11-25 | Sprint 5 | In Progress | 5
CAD Plane | Aidan | 2024-11-18 | 2024-11-25 | Sprint 5 | In Progress | 10
[5 empty] | Total Hours | 22.5
9

## John_Sprint_5
Task | Assignees | Start date | End date | Sprint | Status | Hours Completed | Corrective Action
PSR5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-16 | 2024-11-05 | Sprint 5 | Done | 2
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-11 | 2024-11-11 | Sprint 5 | Done | 1.5
Testing Prototype | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-31 | 2024-11-15 | Sprint 5 | In Progress | 2
Diorama Design | Carly, John | 2024-11-05 | 2024-11-15 | Sprint 5 | In Progress | 4
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-18 | 2024-11-18 | Sprint 5 | Done | 1
MVP2 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-18 | 2024-11-22 | Sprint 5 | In Progress
MVP2 CAD Design | Aidan, Carly, John | 2024-11-18 | 2024-11-22 | Sprint 5 | In Progress
CDR Drawings | Aidan, Carly, John | 2024-11-05 | 2024-11-25 | Sprint 5 | In Progress
CAD Diorama pieces | John | 2024-11-18 | 2024-11-25 | Sprint 5 | In Progress | 10
Diorama Manufacturing | Carly, John | 2024-11-15 | 2024-11-25 | Sprint 5 | In Progress | 5
[5 empty] | Total Hours | 25.5
10

## Sheet1
| Task | Hours
Amber | 15 | 31.5
Diego | 8 | 17.5
Carly | 10 | 20.5
Matthew | 15 | 43.5
Aidan | 9 | 22.5
John | 10 | 25.5