## Amber_Sprint_6
Task | Assignees | Start date | End date | Sprint | Status | Hours Completed | Corrective Action
Practice CDR | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-25 | 2024-10-28 | Sprint 6 | Done | 4
PSR6 | Amber | 2024-11-06 | 2024-11-21 | Sprint 6 | Done | 2
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-25 | 2024-11-25 | Sprint 6 | Done | 1
Finalize Prototype | Matthew, Amber | 2024-11-21 | 2024-11-25 | Sprint 6 | Done | 8
Revise CDR | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-25 | 2024-11-29 | Sprint 6 | Done | 2
CDR Email Sponsor to Review | Amber | 2024-11-29 | 2024-11-29 | Sprint 6 | Done | 0.5
Test Prototype | Matthew, Amber | 2024-11-22 | 2024-11-30 | Sprint 6 | Done | 23
Add bounding box capability to Transmission Protocol | Matthew, Amber | 2024-11-22 | 2024-11-30 | Sprint 6 | Done | 3
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-12-02 | 2024-12-02 | Sprint 6 | Done | 1
CDR/ISR Presentation | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-05 | 2024-12-03 | Sprint 6 | Done | 2
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-12-09 | 2024-12-09 | Sprint 6 | Done | 1
Team Evaluation: Critical Design Review | Aidan, Carly, Diego, John, Matthew, Amber | 2024-12-06 | 2024-12-10 | Sprint 6 | Done | 1
CDR/ISR Team Eval | Aidan, Carly, Diego, John, Matthew, Amber | 2024-12-05 | 2024-12-10 | Sprint 6 | Done | 1
[5 empty] | Total Hours | 49.5
| Task | Hours
Amber | 13 | 49.5
Diego | 8 | 13
Carly | 9 | 17
Matthew | 11 | 47
Aidan | 9 | 17
John | 9 | 17

## Diego_Sprint_6
Task | Assignees | Start date | End date | Sprint | Status | Hours Completed | Corrective Action
Practice CDR | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-25 | 2024-10-28 | Sprint 6 | Done | 4
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-25 | 2024-11-25 | Sprint 6 | Done | 1
Revise CDR | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-25 | 2024-11-29 | Sprint 6 | Done | 2
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-12-02 | 2024-12-02 | Sprint 6 | Done | 1
CDR/ISR Presentation | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-05 | 2024-12-03 | Sprint 6 | Done | 2
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-12-09 | 2024-12-09 | Sprint 6 | Done | 1
Team Evaluation: Critical Design Review | Aidan, Carly, Diego, John, Matthew, Amber | 2024-12-06 | 2024-12-10 | Sprint 6 | Done | 1
CDR/ISR Team Eval | Aidan, Carly, Diego, John, Matthew, Amber | 2024-12-05 | 2024-12-10 | Sprint 6 | Done | 1
[5 empty] | Total Hours | 13

## Carly_Sprint_6
Task | Assignees | Start date | End date | Sprint | Status | Hours Completed | Corrective Action
Practice CDR | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-25 | 2024-10-28 | Sprint 6 | Done | 4
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-25 | 2024-11-25 | Sprint 6 | Done | 1
Revise CDR | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-25 | 2024-11-29 | Sprint 6 | Done | 2
Drawings reviewed and put in CDR | Aidan, Carly, John | 2024-11-27 | 2024-12-02 | Sprint 6 | Todo | 4
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-12-02 | 2024-12-02 | Sprint 6 | Done | 1
CDR/ISR Presentation | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-05 | 2024-12-03 | Sprint 6 | Done | 2
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-12-09 | 2024-12-09 | Sprint 6 | Done | 1
Team Evaluation: Critical Design Review | Aidan, Carly, Diego, John, Matthew, Amber | 2024-12-06 | 2024-12-10 | Sprint 6 | Done | 1
CDR/ISR Team Eval | Aidan, Carly, Diego, John, Matthew, Amber | 2024-12-05 | 2024-12-10 | Sprint 6 | Done | 1
[5 empty] | Total Hours | 17

## Matthew_Sprint_6
Task | Assignees | Start date | End date | Sprint | Status | Hours Completed | Corrective Action
Practice CDR | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-25 | 2024-10-28 | Sprint 6 | Done | 4
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-25 | 2024-11-25 | Sprint 6 | Done | 1
Finalize Prototype | Matthew, Amber | 2024-11-21 | 2024-11-25 | Sprint 6 | Done | 8
Revise CDR | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-25 | 2024-11-29 | Sprint 6 | Done | 2
Test Prototype | Matthew, Amber | 2024-11-22 | 2024-11-30 | Sprint 6 | Done | 23
Add bounding box capability to Transmission Protocol | Matthew, Amber | 2024-11-22 | 2024-11-30 | Sprint 6 | Done | 3
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-12-02 | 2024-12-02 | Sprint 6 | Done | 1
CDR/ISR Presentation | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-05 | 2024-12-03 | Sprint 6 | Done | 2
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-12-09 | 2024-12-09 | Sprint 6 | Done | 1
Team Evaluation: Critical Design Review | Aidan, Carly, Diego, John, Matthew, Amber | 2024-12-06 | 2024-12-10 | Sprint 6 | Done | 1
CDR/ISR Team Eval | Aidan, Carly, Diego, John, Matthew, Amber | 2024-12-05 | 2024-12-10 | Sprint 6 | Done | 1
[5 empty] | Total Hours | 47

## Aidan_Sprint_6
Task | Assignees | Start date | End date | Sprint | Status | Hours Completed | Corrective Action
Practice CDR | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-25 | 2024-10-28 | Sprint 6 | Done | 4
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-25 | 2024-11-25 | Sprint 6 | Done | 1
Revise CDR | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-25 | 2024-11-29 | Sprint 6 | Done | 2
Drawings reviewed and put in CDR | Aidan, Carly, John | 2024-11-27 | 2024-12-02 | Sprint 6 | Todo | 4
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-12-02 | 2024-12-02 | Sprint 6 | Done | 1
CDR/ISR Presentation | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-05 | 2024-12-03 | Sprint 6 | Done | 2
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-12-09 | 2024-12-09 | Sprint 6 | Done | 1
Team Evaluation: Critical Design Review | Aidan, Carly, Diego, John, Matthew, Amber | 2024-12-06 | 2024-12-10 | Sprint 6 | Done | 1
CDR/ISR Team Eval | Aidan, Carly, Diego, John, Matthew, Amber | 2024-12-05 | 2024-12-10 | Sprint 6 | Done | 1
[5 empty] | Total Hours | 17

## John_Sprint_6
Task | Assignees | Start date | End date | Sprint | Status | Hours Completed | Corrective Action
Practice CDR | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-25 | 2024-10-28 | Sprint 6 | Done | 4
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-25 | 2024-11-25 | Sprint 6 | Done | 1
Revise CDR | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-25 | 2024-11-29 | Sprint 6 | Done | 2
Drawings reviewed and put in CDR | Aidan, Carly, John | 2024-11-27 | 2024-12-02 | Sprint 6 | Todo | 4
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-12-02 | 2024-12-02 | Sprint 6 | Done | 1
CDR/ISR Presentation | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-05 | 2024-12-03 | Sprint 6 | Done | 2
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-12-09 | 2024-12-09 | Sprint 6 | Done | 1
Team Evaluation: Critical Design Review | Aidan, Carly, Diego, John, Matthew, Amber | 2024-12-06 | 2024-12-10 | Sprint 6 | Done | 1
CDR/ISR Team Eval | Aidan, Carly, Diego, John, Matthew, Amber | 2024-12-05 | 2024-12-10 | Sprint 6 | Done | 1
[5 empty] | Total Hours | 17