## Sprint Sprint 1
Task | Assignees | Start date | End date | Sprint | Status | Hours Completed | Corrective Action
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-09-02 | 2024-09-02 | Sprint 1 | Done | 1
[5 empty] | Total Hours | 1
[5 empty] | TODO Count | 0
[5 empty] | In Progress Count | 0
[5 empty] | Done Count | 1

## Sprint Sprint 2
Task | Assignees | Start date | End date | Sprint | Status | Hours Completed | Corrective Action
Sponsor meeting @3:30 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-09-04 | 2024-09-04 | Sprint 2 | Done | 0.5
Team Charter | John, Amber | 2024-09-06 | 2024-09-09 | Sprint 2 | Done | 3
Conduct Reseach on Project options | Aidan, Carly, Diego, John, Matthew, Amber | 2024-09-06 | 2024-09-09 | Sprint 2 | Done | 2
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-09-09 | 2024-09-09 | Sprint 2 | Done | 1
Email sponsor ConOps and questions for review | Amber | 2024-09-09 | 2024-09-10 | Sprint 2 | Done | 0.25
Add questions for Jake and Deigo in drive | Aidan, Carly, Diego, John, Matthew, Amber | 2024-09-09 | 2024-09-11 | Sprint 2 | Done | 1
ConOps | Diego, Amber | 2024-09-05 | 2024-09-11 | Sprint 2 | Done | 5
Sponsor meeting @3:30 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-09-11 | 2024-09-11 | Sprint 2 | Done | 0.5
Email professor about sponsor PDR date request for 10/29 to go first | Amber | 2024-09-11 | 2024-09-12 | Sprint 2 | Done | 0.25
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-09-16 | 2024-09-16 | Sprint 2 | Done | 1
Functional Requirements & Functional Block Diagram | Aidan, Diego, Amber | 2024-09-12 | 2024-09-16 | Sprint 2 | Done | 3
PSR2 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-09-06 | 2024-09-17 | Sprint 2 | Done | 2
Sponsor Meeting 3 Questions 9/18/2024 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-09-16 | 2024-09-17 | Sprint 2 | Done | 0.5
Sponsor meeting @3:30 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-09-18 | 2024-09-18 | Sprint 2 | Done | 0.5
Camera angle placement drawing | Carly, John | 2024-09-19 | 2024-09-19 | Sprint 2 | Done | 1
Trades & Point Design | Aidan, Carly, Diego, John, Matthew, Amber | 2024-09-13 | 2024-09-19 | Sprint 2 | Done | 2
figure out scrimmage dates | Aidan | 2024-09-16 | 2024-09-20 | Sprint 2 | Done | 0.25
Email Jake and Diego about Proposal draft | Amber | 2024-09-20 | 2024-09-20 | Sprint 2 | Done | 0.25
Subcontractors and consultants | Matthew | 2024-09-16 | 2024-09-21 | Sprint 2 | Done | 0.25
Key personal- in Proposal | Carly | 2024-09-16 | 2024-09-21 | Sprint 2 | Done | 0.5
Related Work- in proposal | John | 2024-09-16 | 2024-09-21 | Sprint 2 | Done | 1
Signatures and resumes in Proposal | Aidan, Carly, Diego, John, Matthew, Amber | 2024-09-16 | 2024-09-21 | Sprint 2 | Done | 0.5
Customer Furnished Equipment | Aidan | 2024-09-16 | 2024-09-21 | Sprint 2 | Done | 0.5
Data Restriction | Carly | 2024-09-16 | 2024-09-21 | Sprint 2 | Done | 0.25
Facilities/ Equipment in proposal | Aidan | 2024-09-16 | 2024-09-21 | Sprint 2 | Done | 0.5
Statement of Work in Proposal | Amber | 2024-09-16 | 2024-09-21 | Sprint 2 | Done | 0.5
Functional Block Diagram , functional requirements in proposal | Diego, Amber | 2024-09-16 | 2024-09-22 | Sprint 2 | Done | 3
Turn in Proposal | Carly, John, Matthew, Amber | 2024-09-16 | 2024-09-23 | Sprint 2 | Done | 0.25
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-09-23 | 2024-09-23 | Sprint 2 | Done | 1
Set up Reoccurring zoom meeting link with sponsors | Amber | 2024-09-23 | 2024-09-23 | Sprint 2 | Done | 0.25
Get signatures from Sponsors for Proposal | Amber | 2024-09-23 | 2024-09-24 | Sprint 2 | Done | 0.5
Team Evaluation:Proposal | Aidan, Carly, Diego, John, Matthew, Amber | 2024-09-20 | 2024-09-24 | Sprint 2 | Done | 1.75
Get Jim's Signature for Proposal | Amber | 2024-09-23 | 2024-09-24 | Sprint 2 | Done | 0.25
SBD | Carly | 2024-09-19 | 2024-09-26 | Sprint 2 | Done | 2.5
Assign everyone to a part of the Systems Requirement Document | Amber | 2024-09-27 | 2024-09-29 | Sprint 2 | Done | 0.5
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-09-30 | 2024-09-30 | Sprint 2 | Done | 1
Schedule a dry run for PDR | Amber | 2024-09-30 | 2024-09-30 | Sprint 2 | Done
Break up work for PDR and CDR | Amber | 2024-09-30 | 2024-09-30 | Sprint 2 | Done | 1
[5 empty] | Total Hours | 40
[5 empty] | TODO Count | 0
[5 empty] | In Progress Count | 0
[5 empty] | Done Count | 38

## Sprint Sprint 3
Task | Assignees | Start date | End date | Sprint | Status | Hours Completed | Corrective Action
System Requirements Verification Matrix | Diego | 2024-09-26 | 2024-10-01 | Sprint 3 | Done | 1
PSR3 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-09-19 | 2024-10-01 | Sprint 3 | Done | 1.5
Camera Research | Carly | 2024-10-03 | 2024-10-03 | Sprint 3 | Done | 1.5
Camera Equation for prototyping plan | Matthew | 2024-09-30 | 2024-10-03 | Sprint 3 | Done | 0.25
Power Equation for Prototyping Plan | Carly, John | 2024-09-30 | 2024-10-03 | Sprint 3 | Done | 0.5
Requirements Scrimmage slides setup | John | 2024-10-03 | 2024-10-03 | Sprint 3 | Done | 1
Research Project Fundamentals, modeling & Prototype Plan | Aidan, Carly, Diego, John, Matthew, Amber | 2024-09-23 | 2024-10-03 | Sprint 3 | Done | 1.5
Requirements Scrimmage 1 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-09-12 | 2024-10-03 | Sprint 3 | Done | 2.5
Yolo equation for prototyping plan | Amber | 2024-09-30 | 2024-10-03 | Sprint 3 | Done | 0.25
All requirements by system for SRD | Diego, Amber | 2024-09-30 | 2024-10-04 | Sprint 3 | Done | 1.5
verification matrix for SRD | Carly, Diego | 2024-09-30 | 2024-10-04 | Sprint 3 | Done | 1
SRD-Definitions, acronyms, and abbreviations | Aidan | 2024-09-30 | 2024-10-04 | Sprint 3 | Done | 1
SRD-requirements verification | Carly | 2024-09-30 | 2024-10-04 | Sprint 3 | Done | 1
Reference for SRD | John | 2024-09-30 | 2024-10-04 | Sprint 3 | Done | 0.5
SRD-Standards and help out with referenced documents | Matthew | 2024-09-30 | 2024-10-04 | Sprint 3 | Done | 1
Send requirements matrix to Jake and Diego | Amber | 2024-09-30 | 2024-10-04 | Sprint 3 | Done | 0.25
SRD- Reference spec sheet for cameras | Matthew | 2024-09-30 | 2024-10-04 | Sprint 3 | Done | 0.5
Email Jake and Diego about scheduling a tour | Amber | 2024-10-02 | 2024-10-04 | Sprint 3 | Done | 0.25
Email Jake and Diego PDR information | Amber | 2024-10-02 | 2024-10-06 | Sprint 3 | Done | 0.25
System Requirements Document:2.0-Applicable Documents (references in SRD including Standards) | Aidan, Carly, Diego, John, Matthew, Amber | 2024-09-27 | 2024-10-07 | Sprint 3 | Done | 1
System Requirements Document:7.0-Notes | Aidan, Carly, Diego, John, Matthew, Amber | 2024-09-27 | 2024-10-07 | Sprint 3 | Done | 0.5
System Requirements Document: 3.0-Definitions, Acronyms and Abbreviations | Aidan, Carly, Diego, John, Matthew, Amber | 2024-09-27 | 2024-10-07 | Sprint 3 | Done | 0.25
System Requirements Document:6.0-System Requirements Verification Matrix (SRVM) | Aidan, Carly, Diego, John, Matthew, Amber | 2024-09-27 | 2024-10-07 | Sprint 3 | Done | 1
System Requirements Document: 4.0-Requirements | Aidan, Carly, Diego, John, Matthew, Amber | 2024-09-27 | 2024-10-07 | Sprint 3 | Done | 1
System Requirements Document:5.0-Verification Requirements | Aidan, Carly, Diego, John, Matthew, Amber | 2024-09-27 | 2024-10-07 | Sprint 3 | Done | 0.5
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-07 | 2024-10-07 | Sprint 3 | Done | 1
System Requirements Document:8.0-Ability to formulate a design problem for specified needs and technical requirements (O2a) | Aidan, Carly, Diego, John, Matthew, Amber | 2024-09-27 | 2024-10-07 | Sprint 3 | Done | 0.5
Background for scrimmage slides | Aidan | 2024-10-03 | 2024-10-07 | Sprint 3 | Done
Summary for scrimmage slides | Diego | 2024-10-03 | 2024-10-07 | Sprint 3 | Done | 1
Importance and Significance for scrimmage slides | John | 2024-10-03 | 2024-10-07 | Sprint 3 | Done | 1
System Requirements Document: 1.0-Introduction and Scope (Background, Need, ConOps, Stakeholders) | Aidan, Carly, Diego, John, Matthew, Amber | 2024-09-27 | 2024-10-07 | Sprint 3 | Done | 1.5
Requirements Flow Down | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-01 | 2024-10-08 | Sprint 3 | Done | 2
scope for SRD | Amber | 2024-09-30 | 2024-10-08 | Sprint 3 | Done | 0.25
System Requirements Document | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-01 | 2024-10-10 | Sprint 3 | Done | 2
Team Evaluation: System Requirements | Aidan, Carly, Diego, John, Matthew, Amber | 2024-09-27 | 2024-10-10 | Sprint 3 | Done | 0.5
Edit Code for PDR to include individual tasks for each team member with hours | Amber | 2024-10-01 | 2024-10-11 | Sprint 3 | Done | 1
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-14 | 2024-10-14 | Sprint 3 | Done | 1
UX for GUI | Amber | 2024-10-14 | 2024-10-22 | Sprint 3 | Done | 1.5
[5 empty] | Total Hours | 34.75
[5 empty] | TODO Count | 0
[5 empty] | In Progress Count | 0
[5 empty] | Done Count | 38

## Sprint Sprint 4
Task | Assignees | Start date | End date | Sprint | Status | Hours Completed | Corrective Action
Requirements for slides | Amber | 2024-10-03 | 2024-10-07 | Sprint 4 | Done | 0.5
Drawing/SDD | Matthew, Amber | 2024-10-08 | 2024-10-15 | Sprint 4 | Done | 1.5
Verification Procedures | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-08 | 2024-10-15 | Sprint 4 | Done | 0.5
Minimum Viable Product Definition | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-08 | 2024-10-15 | Sprint 4 | Done | 2
PSR4 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-02 | 2024-10-15 | Sprint 4 | Done | 4
GUI UI for PDR | Amber | 2024-10-15 | 2024-10-18 | Sprint 4 | Done | 0.5
MVP CAD drawings for PDR | Carly | 2024-10-15 | 2024-10-18 | Sprint 4 | Done | 1
Key components selected for PDR | Aidan, Carly | 2024-10-15 | 2024-10-20 | Sprint 4 | Done | 1
Risk/Mitigation for PDR | Amber | 2024-10-15 | 2024-10-20 | Sprint 4 | Done | 1
Project Plan, Status, Deliverables, & Budget Analysis for PDR | Diego, Amber | 2024-10-15 | 2024-10-20 | Sprint 4 | Done | 1
Software/firmware for PDR | Matthew, Amber | 2024-10-15 | 2024-10-20 | Sprint 4 | Done | 2
Initial physical configuration for PDR | Aidan, Carly | 2024-10-15 | 2024-10-20 | Sprint 4 | Done | 1
PDR Presentation | Aidan, Carly, Diego, John, Matthew, Amber | 2024-09-24 | 2024-10-21 | Sprint 4 | Done | 2
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-21 | 2024-10-21 | Sprint 4 | Done | 1
MVP SolidWorks Base Assembly | John | 2024-10-20 | 2024-10-21 | Sprint 4 | Done | 5.5
Electrical Schematic PDR | John | 2024-10-20 | 2024-10-21 | Sprint 4 | Done | 1
PDR Point Design CAD | Aidan, Carly, John | 2024-10-18 | 2024-10-21 | Sprint 4 | Done | 10
PDR Dry Run | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-21 | 2024-10-21 | Sprint 4 | Done | 1
PDR Slides Review | Carly | 2024-10-18 | 2024-10-22 | Sprint 4 | Done | 5
Preliminary Design Review Presentation | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-08 | 2024-10-22 | Sprint 4 | Done | 5
Update Electronics Schematic PDR | John | 2024-10-21 | 2024-10-22 | Sprint 4 | Done | 1
PDR Key Components and Trade | Carly | 2024-10-17 | 2024-10-22 | Sprint 4 | Done | 1
PDR System Block Diagram | Carly | 2024-10-14 | 2024-10-22 | Sprint 4 | Done | 0.25
PDR Design Concept | Carly | 2024-10-14 | 2024-10-22 | Sprint 4 | Done | 4
PDR Key Components | Carly | 2024-10-14 | 2024-10-22 | Sprint 4 | Done | 2
PDR MVP1 | Carly | 2024-10-14 | 2024-10-22 | Sprint 4 | Done | 3
Risk/Mitigation | Amber | 2024-10-15 | 2024-10-22 | Sprint 4 | Done | 1
Requirements Slide PDR | Amber | 2024-10-14 | 2024-10-22 | Sprint 4 | Done | 0.5
Communication TPD Slide PDR | Amber | 2024-10-15 | 2024-10-22 | Sprint 4 | Done | 0.5
Project Deliverable Slide | Amber | 2024-10-15 | 2024-10-22 | Sprint 4 | Done | 1
PDR Summary Slide | Amber | 2024-10-15 | 2024-10-22 | Sprint 4 | Done | 0.5
1st Order Analysis: Cameras Slide PDR | Carly, Amber | 2024-10-15 | 2024-10-22 | Sprint 4 | Done | 0.5
PDR Slides | John | 2024-10-15 | 2024-10-22 | Sprint 4 | Done | 5.5
Project Plan to CDR Slide | Amber | 2024-10-15 | 2024-10-22 | Sprint 4 | Done | 1
PDR Team Eval | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-22 | 2024-10-28 | Sprint 4 | Done | 1
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-28 | 2024-10-28 | Sprint 4 | Done | 1
Team Evaluation: Preliminary Design Review | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-25 | 2024-10-29 | Sprint 4 | Done | 1
Team Evaluation: System Requirements | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-25 | 2024-10-29 | Sprint 4 | Done | 1
PDR Personal Run Thru and Review | John | 2024-10-22 | 2024-10-29 | Sprint 4 | Done | 3
Implement Basic Reverse Projection Algorithm | Matthew | 2024-10-18 | 2024-10-31 | Sprint 4 | Done | 20
Prototype Static Tensor Algorithm Generation | Matthew | 2024-09-24 | 2024-10-31 | Sprint 4 | Done | 40
Prototype and GUI Development | Matthew, Amber | 2024-10-21 | 2024-11-03 | Sprint 4 | Done | 2
Add Static Image Server Routes | Matthew | 2024-10-30 | 2024-11-04 | Sprint 4 | Done | 1
Generalize Stitching FrameBuffers for Cameras | Matthew | 2024-10-29 | 2024-11-04 | Sprint 4 | Done | 3
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-04 | 2024-11-04 | Sprint 4 | Done | 1.5
Setup Websocket Connection Framework | Matthew | 2024-11-01 | 2024-11-04 | Sprint 4 | Done | 1
Begin Planning for Client-Server Connection Protocol | Matthew | 2024-10-31 | 2024-11-04 | Sprint 4 | Done | 0.5
Review and Discuss Action Items | John | 2024-11-04 | 2024-11-04 | Sprint 4 | Done | 0.5
Review broken down dates for PDR to CDR update | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-05 | 2024-11-05 | Sprint 4 | Done | 1
Email ECE Connections for Electrical System Review | John | 2024-11-04 | 2024-11-05 | Sprint 4 | Done | 0.5
Research Batteries | John | 2024-11-04 | 2024-11-05 | Sprint 4 | Done | 0.5
Scope for PDR | Amber | 2024-10-14 | 2024-11-22 | Sprint 4 | Done | 0.25
[5 empty] | Total Hours | 147
[5 empty] | TODO Count | 0
[5 empty] | In Progress Count | 0
[5 empty] | Done Count | 52

## Sprint Sprint 6
Task | Assignees | Start date | End date | Sprint | Status | Hours Completed | Corrective Action
Practice CDR | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-25 | 2024-10-28 | Sprint 6 | Done | 4
PSR6 | Amber | 2024-11-06 | 2024-11-21 | Sprint 6 | Done | 2
Finalize Prototype | Matthew, Amber | 2024-11-21 | 2024-11-25 | Sprint 6 | Done | 8
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-25 | 2024-11-25 | Sprint 6 | Done | 1
Revise CDR | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-25 | 2024-11-29 | Sprint 6 | Done | 2
CDR Email Sponsor to Review | Amber | 2024-11-29 | 2024-11-29 | Sprint 6 | Done | 0.5
Test Prototype | Matthew, Amber | 2024-11-22 | 2024-11-30 | Sprint 6 | Done | 23
Add bounding box capability to Transmission Protocol | Matthew, Amber | 2024-11-22 | 2024-11-30 | Sprint 6 | Done | 3
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-12-02 | 2024-12-02 | Sprint 6 | Done | 1
Drawings reviewed and put in CDR | Aidan, Carly, John | 2024-11-27 | 2024-12-02 | Sprint 6 | Done | 4
CDR/ISR Presentation | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-05 | 2024-12-03 | Sprint 6 | Done | 2
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-12-09 | 2024-12-09 | Sprint 6 | Done | 1
Team Evaluation: Critical Design Review | Aidan, Carly, Diego, John, Matthew, Amber | 2024-12-06 | 2024-12-10 | Sprint 6 | Done | 1
CDR/ISR Team Eval | Aidan, Carly, Diego, John, Matthew, Amber | 2024-12-05 | 2024-12-10 | Sprint 6 | Done | 1
[5 empty] | Total Hours | 53.5
[5 empty] | TODO Count | 0
[5 empty] | In Progress Count | 0
[5 empty] | Done Count | 14

## Sprint Sprint 5
Task | Assignees | Start date | End date | Sprint | Status | Hours Completed | Corrective Action
PSR5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-16 | 2024-11-05 | Sprint 5 | Done | 2
Fix Framebuffer Update Regression | Matthew | 2024-11-04 | 2024-11-06 | Sprint 5 | Done | 3
Primitive Live Loading Capability | Matthew, Amber | 2024-11-04 | 2024-11-08 | Sprint 5 | Done | 4
Basic Server Video Transmission | Matthew | 2024-11-04 | 2024-11-10 | Sprint 5 | Done | 6
Have GUI prototype | Amber | 2024-11-04 | 2024-11-10 | Sprint 5 | Done | 4
Determine Transmission Protocol Definition | Matthew | 2024-11-08 | 2024-11-10 | Sprint 5 | Done | 2
Basic UI Video Transmission | Amber | 2024-11-04 | 2024-11-10 | Sprint 5 | Done | 2
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-11 | 2024-11-11 | Sprint 5 | Done | 1.5
Parker Meggit Tour | Aidan, Diego, Matthew, Amber | 2024-11-12 | 2024-11-12 | Sprint 5 | Done | 1
Refine Live Loading Implementation | Matthew | 2024-11-06 | 2024-11-12 | Sprint 5 | Done | 15
Add UI controls | Amber | 2024-11-06 | 2024-11-14 | Sprint 5 | Done | 2
Determine Controls API Definition | Matthew, Amber | 2024-11-06 | 2024-11-14 | Sprint 5 | Done | 1
Diorama Design | Carly, John | 2024-11-05 | 2024-11-15 | Sprint 5 | Done | 4
Testing Prototype | Aidan, Carly, Diego, John, Matthew, Amber | 2024-10-31 | 2024-11-15 | Sprint 5 | Done | 2
Team Meeting @ 5 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-18 | 2024-11-18 | Sprint 5 | Done | 1
Transfer slides from PDR to CDR | Diego, Amber | 2024-11-18 | 2024-11-22 | Sprint 5 | Done | 5
MVP2 CAD Design | Aidan, Carly, John | 2024-11-18 | 2024-11-22 | Sprint 5 | Done | 12
Update slides CDR Slides | Diego, Amber | 2024-11-18 | 2024-11-22 | Sprint 5 | Done | 5
Add Server Endpoints for controls | Matthew | 2024-11-06 | 2024-11-22 | Sprint 5 | Done | 5
Update Risks | Amber | 2024-11-18 | 2024-11-22 | Sprint 5 | Done | 1
MVP2 | Aidan, Carly, Diego, John, Matthew, Amber | 2024-11-18 | 2024-11-22 | Sprint 5 | Done | 15
Switch to GPU Projection | Matthew | 2024-11-11 | 2024-11-25 | Sprint 5 | Done | 7
CAD Diorama pieces | John | 2024-11-18 | 2024-11-25 | Sprint 5 | Done | 10
Diorama Manufacturing | Carly, John | 2024-11-15 | 2024-11-25 | Sprint 5 | Done
CAD- Mounting brackets for all electronics | Carly | 2024-11-15 | 2024-11-25 | Sprint 5 | Done | 10
CAD Plane | Aidan | 2024-11-18 | 2024-11-25 | Sprint 5 | Done | 10
CDR Drawings | Aidan, Carly, John | 2024-11-05 | 2024-11-25 | Sprint 5 | Done
[5 empty] | Total Hours | 130.5
[5 empty] | TODO Count | 0
[5 empty] | In Progress Count | 0
[5 empty] | Done Count | 27

## Sprint Sprint 10
Task | Assignees | Start date | End date | Sprint | Status | Hours Completed | Corrective Action
Add Video Compression to server and client, if necessary | Matthew, Amber | 2024-11-22 | 2024-11-30 | Sprint 10 | Done | 2
Print 3rd model if needed | Aidan, Carly, John | 2025-02-19 | 2025-02-21 | Sprint 10 | Todo
Action Items | Diego, Amber | 2025-02-18 | 2025-02-21 | Sprint 10 | Done | 5
Create CASA Object File | John | 2025-02-17 | 2025-02-21 | Sprint 10 | Done | 0.5
Round of Testing After ISR Practice | Aidan, Carly, Diego, John, Matthew, Amber | 2025-02-18 | 2025-02-22 | Sprint 10 | Done | 2
ISR Weight Budget Slide | John | 2025-02-22 | 2025-02-23 | Sprint 10 | Done | 1
ISR Mass Table Slide + Values | John | 2025-02-22 | 2025-02-23 | Sprint 10 | Done | 1
ISR TopBack/Tail/Elevator Part Modifications Slides | John | 2025-02-22 | 2025-02-23 | Sprint 10 | Done | 2.5
Start Running through plan tests | Matthew, Amber | 2025-02-19 | 2025-02-25 | Sprint 10 | In Progress
ISR2 Slides | Diego, Amber | 2025-02-15 | 2025-02-25 | Sprint 10 | Done | 5
Sponsor meeting | Aidan, Carly, Diego, John, Matthew, Amber | 2025-02-26 | 2025-02-26 | Sprint 10 | Done | 0.5
TDP Document 2 | Amber | 2025-02-01 | 2025-03-01 | Sprint 10 | Done | 5
Update SOLIDWORKS Drawings for TDP 2 | John | 2025-03-03 | 2025-03-04 | Sprint 10 | Done | 1.5
ISR Slide Practice | John | 2025-03-02 | 2025-03-04 | Sprint 10 | Done | 3.5
TE-(ISR2 & TDP) | Aidan, Carly, Diego, John, Matthew, Amber | 2025-03-01 | 2025-03-05 | Sprint 10 | Done | 1
Sponsor meeting | Aidan, Carly, Diego, John, Matthew, Amber | 2025-02-19 | 2025-03-19 | Sprint 10 | Done | 0.5
TDP finalize | Carly |  |  | Sprint 10 | Done | 2
ISR practice | Carly |  |  | Sprint 10 | Done | 5
Calibrate New Cameras/Plane | Matthew |  |  | Sprint 10 | In Progress | 4
Experiment with Auto Calibration Software | Matthew |  |  | Sprint 10 | In Progress | 5
Setup model rendering for the new plane | Matthew |  |  | Sprint 10 | Done | 3
Create masks for PlaneV2 | Matthew |  |  | Sprint 10 | Done | 2
Create more ergonomic config and world bounds | Matthew |  |  | Sprint 10 | Done | 5
[5 empty] | Total Hours | 57
[5 empty] | TODO Count | 1
[5 empty] | In Progress Count | 3
[5 empty] | Done Count | 19

## Sprint Sprint 7
Task | Assignees | Start date | End date | Sprint | Status | Hours Completed | Corrective Action
Create TensorRT bindings | Matthew | 2024-12-16 | 2025-01-10 | Sprint 7 | Done | 15
Create YOLO model with channel conversion | Matthew | 2024-12-16 | 2025-01-10 | Sprint 7 | Done | 3
Setup Jetson | Matthew | 2024-12-16 | 2025-01-10 | Sprint 7 | Done | 10
Research CSI/USB3 Cameras | Aidan, Carly, Diego, John, Matthew, Amber | 2025-01-13 | 2025-01-17 | Sprint 7 | Done
[5 empty] | Total Hours | 28
[5 empty] | TODO Count | 0
[5 empty] | In Progress Count | 0
[5 empty] | Done Count | 4

## Sprint Sprint 8
Task | Assignees | Start date | End date | Sprint | Status | Hours Completed | Corrective Action
Plane 3d Print One | Aidan, Carly | 2025-01-17 | 2025-01-19 | Sprint 8 | Done
SDD review before changes | Matthew, Amber | 2025-01-17 | 2025-01-19 | Sprint 8 | Done | 1
Fit 3d print with system | Matthew | 2025-01-20 | 2025-01-20 | Sprint 8 | Done | 1
TDP1 Document | Aidan, Carly, Diego, John, Matthew, Amber | 2025-01-13 | 2025-01-22 | Sprint 8 | Done | 6
SDD requirments | Amber | 2025-01-20 | 2025-01-24 | Sprint 8 | Done | 3
Redo SDD | Amber | 2025-01-21 | 2025-01-24 | Sprint 8 | Done | 7
Object detection implementation | Matthew, Amber | 2025-01-22 | 2025-01-25 | Sprint 8 | Done | 10
TDP Document Review | Amber | 2025-01-19 | 2025-01-25 | Sprint 8 | Done | 3
Test Plan | Amber | 2025-01-22 | 2025-01-25 | Sprint 8 | Done | 3
Plane Re-Design (John) | John | 2025-01-24 | 2025-01-26 | Sprint 8 | Done | 26
Plane Re-Design (Aidan) | Aidan | 2025-01-24 | 2025-01-26 | Sprint 8 | Done | 26
Plane Re-Design (Carly) | Carly | 2025-01-24 | 2025-01-26 | Sprint 8 | Done | 26
Test Verification update/redo | Amber | 2025-01-22 | 2025-01-26 | Sprint 8 | Done | 2
Indentured Drawing List Update | Carly | 2025-01-16 | 2025-01-28 | Sprint 8 | Done | 1
CASA Drawings (Carly) | Carly | 2025-01-26 | 2025-01-28 | Sprint 8 | Done | 4
Diorama Ground Vehicles Revisions & Drawings (John) | John | 2025-01-26 | 2025-01-28 | Sprint 8 | Done | 2
MVP Drawings (John) | John | 2025-01-26 | 2025-01-28 | Sprint 8 | Done | 2
Exploded CASA Drawing (Aidan) | Aidan | 2025-01-26 | 2025-01-28 | Sprint 8 | Done | 1
Graphic and better metric test | Amber | 2025-01-27 | 2025-01-28 | Sprint 8 | Done | 2
PSR 8 | Amber | 2025-01-28 | 2025-01-30 | Sprint 8 | Done | 2
Create Argus bindings | Matthew | 2025-01-29 | 2025-01-31 | Sprint 8 | Done | 6
Improve software error handling recovery | Matthew | 2025-01-17 | 2025-02-06 | Sprint 8 | Done | 2
Integrate new cameras into software | Matthew | 2025-01-24 | 2025-02-06 | Sprint 8 | Done | 10
[5 empty] | Total Hours | 146
[5 empty] | TODO Count | 0
[5 empty] | In Progress Count | 0
[5 empty] | Done Count | 23

## Sprint Sprint 9
Task | Assignees | Start date | End date | Sprint | Status | Hours Completed | Corrective Action
Check in status of Camera integration | Matthew, Amber | 2025-01-31 | 2025-01-31 | Sprint 9 | Done | 0.5
Verification Table | Diego, Amber | 2025-02-01 | 2025-02-04 | Sprint 9 | Done | 2
Print 1st Model | Aidan, Carly, John | 2025-02-02 | 2025-02-05 | Sprint 9 | Done | 10
Sponsor Meeting | Aidan, Carly, Diego, John, Matthew, Amber | 2025-02-05 | 2025-02-05 | Sprint 9 | Done | 1
ReModel | Aidan, Carly, John | 2025-01-31 | 2025-02-06 | Sprint 9 | Done | 17
Integrate Object detection | Matthew | 2025-02-03 | 2025-02-09 | Sprint 9 | Done | 15
Print 2nd Model if needed | Aidan, Carly, John | 2025-02-09 | 2025-02-11 | Sprint 9 | Todo | 10
Sponsor Meeting | Aidan, Carly, Diego, John, Matthew, Amber | 2025-02-12 | 2025-02-12 | Sprint 9 | Done | 0.5
Design Day Booklet description | Diego, Amber | 2025-02-11 | 2025-02-13 | Sprint 9 | Done | 1.5
Correct 3D image if needed | Aidan, Carly, John | 2025-02-13 | 2025-02-14 | Sprint 9 | Todo | 4
Correct 3D model if needed 3rd time | Aidan, Carly, John | 2025-02-14 | 2025-02-18 | Sprint 9 | Todo | 4
3rd Redesign | Aidan, Carly, John | 2025-02-18 | 2025-02-18 | Sprint 9 | In Progress | 6
Debug Argus | Matthew | 2025-02-11 | 2025-02-18 | Sprint 9 | Done | 30
[5 empty] | Total Hours | 101.5
[5 empty] | TODO Count | 3
[5 empty] | In Progress Count | 1
[5 empty] | Done Count | 9

## Sprint Sprint 11
Task | Assignees | Start date | End date | Sprint | Status | Hours Completed | Corrective Action
Pick Fan for Heat Management | Aidan, Carly, Diego, John, Matthew, Amber | 2025-03-06 | 2025-03-09 | Sprint 11 | Todo
360 Degree Birds eye view VTP | Aidan, Carly, Diego, John, Matthew, Amber | 2025-03-03 | 2025-03-14 | Sprint 11 | Todo
Camera Stitching Verification | Matthew | 2025-03-05 | 2025-03-14 | Sprint 11 | Todo
Real-Time View Update VTP | Matthew | 2025-03-06 | 2025-03-14 | Sprint 11 | Todo
Update Camera Mount Angles on TopBack Part | Aidan, Carly, John | 2025-03-06 | 2025-03-17 | Sprint 11 | Todo
Update Nose, BottomMiddle, TopMiddle, BottomBack, and Wing Parts to Incorporate Fan and Reduce Blind Spots | Aidan, Carly, John | 2025-03-06 | 2025-03-17 | Sprint 11 | Todo
3D-Print CASA 6.0 | Aidan, Carly, John, Amber | 2025-03-16 | 2025-03-19 | Sprint 11 | Todo
Sponsor Meeting | Aidan, Carly, Diego, John, Matthew, Amber | 2025-03-19 | 2025-03-19 | Sprint 11 | Todo
3D-Print All Diorama Pieces (Parker Meggitt) | Aidan, Carly, John | 2025-03-06 | 2025-03-20 | Sprint 11 | Todo
Collision Risk Visual VTP | Matthew, Amber | 2025-03-14 | 2025-03-21 | Sprint 11 | Todo
Object Detection & Labeling VTP | Matthew, Amber | 2025-03-14 | 2025-03-21 | Sprint 11 | Todo
Refine and Change CASA 6.0 as Needed | Aidan, Carly, John | 2025-03-19 | 2025-03-21 | Sprint 11 | Todo
Purchase Necessary Diorama Pieces | Aidan, Carly, Diego, John | 2025-03-16 | 2025-03-23 | Sprint 11 | Todo
Re-Print CASA 6.0 (if needed) | Aidan, Carly, John, Amber | 2025-03-19 | 2025-03-24 | Sprint 11 | Todo
Camera view SRVM | Aidan, Carly, Diego, John, Matthew, Amber | 2025-03-21 | 2025-03-25 | Sprint 11 | Todo
Functionality Verification SRVM | Aidan, Carly, Diego, John, Matthew, Amber | 2025-03-21 | 2025-03-25 | Sprint 11 | Todo
Enviornmental Tests | Aidan, Carly, Diego, John, Matthew, Amber | 2025-03-21 | 2025-03-25 | Sprint 11 | Todo
Assemble Full Diorama | Aidan, Carly, John | 2025-03-23 | 2025-03-29 | Sprint 11 | Todo
Begin Final Acceptance Testing | Aidan, Carly, Diego, John, Matthew, Amber | 2025-03-30 | 2025-04-05 | Sprint 11 | Todo
[5 empty] | Total Hours | 0
[5 empty] | TODO Count | 19
[5 empty] | In Progress Count | 0
[5 empty] | Done Count | 0

## Overall Status Summary
Status | Count
TODO | 23
In Progress | 4 | Sprint | Todo | In Progress | Done
Done | 225 | Sprint 1 | 0 | 0 | 1
|  | Sprint 2 | 0 | 0 | 38
|  | Sprint 3 | 0 | 0 | 38
|  | Sprint 4 | 0 | 0 | 52
|  | Sprint 5 | 0 | 0 | 27
|  | Sprint 6 | 0 | 0 | 14
|  | Sprint 7 | 0 | 0 | 4
|  | Sprint 8 | 0 | 0 | 23
|  | Sprint 9 | 0 | 0 | 13
|  | Sprint 10 | 1 | 3 | 19