## Amber_Sprint_10
Task | Assignees | Start date | End date | Sprint | Status | Hours Completed | Corrective Action
Add Video Compression to server and client, if necessary | Matthew, Amber | 2024-11-22 | 2024-11-30 | Sprint 10 | Done | 2
Action Items | Diego, Amber | 2025-02-18 | 2025-02-21 | Sprint 10 | Done | 5
Round of Testing After ISR Practice | Aidan, Carly, Diego, John, Matthew, Amber | 2025-02-18 | 2025-02-22 | Sprint 10 | Done | 2
Start Running through plan tests | Matthew, Amber | 2025-02-19 | 2025-02-25 | Sprint 10 | In Progress
ISR2 Slides | Diego, Amber | 2025-02-15 | 2025-02-25 | Sprint 10 | Done | 5
Sponsor meeting | Aidan, Carly, Diego, John, Matthew, Amber | 2025-02-26 | 2025-02-26 | Sprint 10 | Done | 0.5
TDP Document 2 | Amber | 2025-02-01 | 2025-03-01 | Sprint 10 | Done | 5
TE-(ISR2 & TDP) | Aidan, Carly, Diego, John, Matthew, Amber | 2025-03-01 | 2025-03-05 | Sprint 10 | Done | 1
Sponsor meeting | Aidan, Carly, Diego, John, Matthew, Amber | 2025-02-19 | 2025-03-19 | Sprint 10 | Done | 0.5
[5 empty] | Total Hours | 21 | Total Tasks | 9

## Diego_Sprint_10
Task | Assignees | Start date | End date | Sprint | Status | Hours Completed | Corrective Action
Action Items | Diego, Amber | 2025-02-18 | 2025-02-21 | Sprint 10 | Done | 5
Round of Testing After ISR Practice | Aidan, Carly, Diego, John, Matthew, Amber | 2025-02-18 | 2025-02-22 | Sprint 10 | Done | 2
ISR2 Slides | Diego, Amber | 2025-02-15 | 2025-02-25 | Sprint 10 | Done | 5
Sponsor meeting | Aidan, Carly, Diego, John, Matthew, Amber | 2025-02-26 | 2025-02-26 | Sprint 10 | Done | 0.5
TE-(ISR2 & TDP) | Aidan, Carly, Diego, John, Matthew, Amber | 2025-03-01 | 2025-03-05 | Sprint 10 | Done | 1
Sponsor meeting | Aidan, Carly, Diego, John, Matthew, Amber | 2025-02-19 | 2025-03-19 | Sprint 10 | Done | 0.5
[5 empty] | Total Hours | 14 | Total Tasks | 6

## Carly_Sprint_10
Task | Assignees | Start date | End date | Sprint | Status | Hours Completed | Corrective Action
Print 3rd model if needed | Aidan, Carly, John | 2025-02-19 | 2025-02-21 | Sprint 10 | Todo
Round of Testing After ISR Practice | Aidan, Carly, Diego, John, Matthew, Amber | 2025-02-18 | 2025-02-22 | Sprint 10 | Done | 2
Sponsor meeting | Aidan, Carly, Diego, John, Matthew, Amber | 2025-02-26 | 2025-02-26 | Sprint 10 | Done | 0.5
TE-(ISR2 & TDP) | Aidan, Carly, Diego, John, Matthew, Amber | 2025-03-01 | 2025-03-05 | Sprint 10 | Done | 1
Sponsor meeting | Aidan, Carly, Diego, John, Matthew, Amber | 2025-02-19 | 2025-03-19 | Sprint 10 | Done | 0.5
TDP finalize | Carly |  |  | Sprint 10 | Done | 2
ISR practice | Carly |  |  | Sprint 10 | Done | 5
[5 empty] | Total Hours | 11 | Total Tasks | 7

## Matthew_Sprint_10
Task | Assignees | Start date | End date | Sprint | Status | Hours Completed | Corrective Action
Add Video Compression to server and client, if necessary | Matthew, Amber | 2024-11-22 | 2024-11-30 | Sprint 10 | Done | 2
Round of Testing After ISR Practice | Aidan, Carly, Diego, John, Matthew, Amber | 2025-02-18 | 2025-02-22 | Sprint 10 | Done | 2
Start Running through plan tests | Matthew, Amber | 2025-02-19 | 2025-02-25 | Sprint 10 | In Progress
Sponsor meeting | Aidan, Carly, Diego, John, Matthew, Amber | 2025-02-26 | 2025-02-26 | Sprint 10 | Done | 0.5
TE-(ISR2 & TDP) | Aidan, Carly, Diego, John, Matthew, Amber | 2025-03-01 | 2025-03-05 | Sprint 10 | Done | 1
Sponsor meeting | Aidan, Carly, Diego, John, Matthew, Amber | 2025-02-19 | 2025-03-19 | Sprint 10 | Done | 0.5
Calibrate New Cameras/Plane | Matthew |  |  | Sprint 10 | In Progress | 4
Experiment with Auto Calibration Software | Matthew |  |  | Sprint 10 | In Progress | 5
Setup model rendering for the new plane | Matthew |  |  | Sprint 10 | Done | 3
Create masks for PlaneV2 | Matthew |  |  | Sprint 10 | Done | 2
Create more ergonomic config and world bounds | Matthew |  |  | Sprint 10 | Done | 5
[5 empty] | Total Hours | 25 | Total Tasks | 11

## Aidan_Sprint_10
Task | Assignees | Start date | End date | Sprint | Status | Hours Completed | Corrective Action
Print 3rd model if needed | Aidan, Carly, John | 2025-02-19 | 2025-02-21 | Sprint 10 | Todo
Round of Testing After ISR Practice | Aidan, Carly, Diego, John, Matthew, Amber | 2025-02-18 | 2025-02-22 | Sprint 10 | Done | 2
Sponsor meeting | Aidan, Carly, Diego, John, Matthew, Amber | 2025-02-26 | 2025-02-26 | Sprint 10 | Done | 0.5
TE-(ISR2 & TDP) | Aidan, Carly, Diego, John, Matthew, Amber | 2025-03-01 | 2025-03-05 | Sprint 10 | Done | 1
Sponsor meeting | Aidan, Carly, Diego, John, Matthew, Amber | 2025-02-19 | 2025-03-19 | Sprint 10 | Done | 0.5
[5 empty] | Total Hours | 4 | Total Tasks | 5

## John_Sprint_10
Task | Assignees | Start date | End date | Sprint | Status | Hours Completed | Corrective Action
Print 3rd model if needed | Aidan, Carly, John | 2025-02-19 | 2025-02-21 | Sprint 10 | Todo
Create CASA Object File | John | 2025-02-17 | 2025-02-21 | Sprint 10 | Done | 0.5
Round of Testing After ISR Practice | Aidan, Carly, Diego, John, Matthew, Amber | 2025-02-18 | 2025-02-22 | Sprint 10 | Done | 2
ISR Weight Budget Slide | John | 2025-02-22 | 2025-02-23 | Sprint 10 | Done | 1
ISR Mass Table Slide + Values | John | 2025-02-22 | 2025-02-23 | Sprint 10 | Done | 1
ISR TopBack/Tail/Elevator Part Modifications Slides | John | 2025-02-22 | 2025-02-23 | Sprint 10 | Done | 2.5
Sponsor meeting | Aidan, Carly, Diego, John, Matthew, Amber | 2025-02-26 | 2025-02-26 | Sprint 10 | Done | 0.5
Update SOLIDWORKS Drawings for TDP 2 | John | 2025-03-03 | 2025-03-04 | Sprint 10 | Done | 1.5
ISR Slide Practice | John | 2025-03-02 | 2025-03-04 | Sprint 10 | Done | 3.5
TE-(ISR2 & TDP) | Aidan, Carly, Diego, John, Matthew, Amber | 2025-03-01 | 2025-03-05 | Sprint 10 | Done | 1
Sponsor meeting | Aidan, Carly, Diego, John, Matthew, Amber | 2025-02-19 | 2025-03-19 | Sprint 10 | Done | 0.5
[5 empty] | Total Hours | 14 | Total Tasks | 11

## Team Summary
Team Member | Task | Hours
Amber | 9 | 21
John | 11 | 14
Carly | 7 | 11
Aidan | 5 | 4
Matthew | 11 | 25
Diego | 6 | 14