## Amber_Sprint_11
Task | Assignees | Start date | End date | Sprint | Status | Hours Completed | Corrective Action
Pick Fan for Heat Management | Aidan, Carly, Diego, John, Matthew, Amber | 2025-03-06 | 2025-03-09 | Sprint 11 | Done | 0.5
360 Degree Birds eye view VTP | Aidan, Carly, Diego, John, Matthew, Amber | 2025-03-03 | 2025-03-14 | Sprint 11 | Todo | 2
Sponsor Meeting | Aidan, Carly, Diego, John, Matthew, Amber | 2025-03-19 | 2025-03-19 | Sprint 11 | Todo | 0.5
3D-Print CASA 6.0 | Aidan, Carly, John, Amber | 2025-03-16 | 2025-03-19 | Sprint 11 | In Progress | 2
3D-Print All Diorama Pieces (Parker Meggitt) | Amber | 2025-03-06 | 2025-03-20 | Sprint 11 | Done | 0.5
Object Detection & Labeling VTP | Matthew, Amber | 2025-03-14 | 2025-03-21 | Sprint 11 | In Progress | 2
Re-Print CASA 6.0 (if needed) | Aidan, Carly, John, Amber | 2025-03-19 | 2025-03-24 | Sprint 11 | In Progress | 5
Enviornmental Tests | Aidan, Carly, Diego, John, Matthew, Amber | 2025-03-21 | 2025-03-25 | Sprint 11 | Done | 1
Camera view SRVM | Aidan, Carly, Diego, John, Matthew, Amber | 2025-03-21 | 2025-03-25 | Sprint 11 | Todo
Functionality Verification SRVM | Aidan, Carly, Diego, John, Matthew, Amber | 2025-03-21 | 2025-03-25 | Sprint 11 | Todo
Sponsor meeting | Aidan, Carly, Diego, John, Matthew, Amber | 2025-03-26 | 2025-03-26 | Sprint 11 | Done | 0.5
SDD Update | Amber | 2025-03-26 | 2025-03-29 | Sprint 11 | Done | 5
4 Nominations | Amber | 2025-03-29 | 2025-03-31 | Sprint 11 | Done | 4
[5 empty] | Total Hours | 23 | Total Tasks | 13

## Diego_Sprint_11
Task | Assignees | Start date | End date | Sprint | Status | Hours Completed | Corrective Action
Pick Fan for Heat Management | Aidan, Carly, Diego, John, Matthew, Amber | 2025-03-06 | 2025-03-09 | Sprint 11 | Done | 0.5
360 Degree Birds eye view VTP | Aidan, Carly, Diego, John, Matthew, Amber | 2025-03-03 | 2025-03-14 | Sprint 11 | Todo | 2
Sponsor Meeting | Aidan, Carly, Diego, John, Matthew, Amber | 2025-03-19 | 2025-03-19 | Sprint 11 | Todo | 0.5
Enviornmental Tests | Aidan, Carly, Diego, John, Matthew, Amber | 2025-03-21 | 2025-03-25 | Sprint 11 | Done | 1
Camera view SRVM | Aidan, Carly, Diego, John, Matthew, Amber | 2025-03-21 | 2025-03-25 | Sprint 11 | Todo
Functionality Verification SRVM | Aidan, Carly, Diego, John, Matthew, Amber | 2025-03-21 | 2025-03-25 | Sprint 11 | Todo
Sponsor meeting | Aidan, Carly, Diego, John, Matthew, Amber | 2025-03-26 | 2025-03-26 | Sprint 11 | Done | 0.5
Purchase Necessary Diorama Pieces | Aidan, Carly, Diego, John | 2025-04-01 | 2025-04-02 | Sprint 11 | Todo | 0.5
write award nominations for social impact and best pres | Diego |  |  | Sprint 11 | Done | 2
draft design day poster | Diego |  |  | Sprint 11 | Done | 1
order fans and filament | Diego |  |  | Sprint 11 | Done | 0.5
[5 empty] | Total Hours | 8.5 | Total Tasks | 11

## Carly_Sprint_11
Task | Assignees | Start date | End date | Sprint | Status | Hours Completed | Corrective Action
Pick Fan for Heat Management | Aidan, Carly, Diego, John, Matthew, Amber | 2025-03-06 | 2025-03-09 | Sprint 11 | Done | 0.5
360 Degree Birds eye view VTP | Aidan, Carly, Diego, John, Matthew, Amber | 2025-03-03 | 2025-03-14 | Sprint 11 | Todo | 2
Update Nose, BottomMiddle, TopMiddle, BottomBack, and Wing Parts to Incorporate Fan and Reduce Blind Spots | Aidan, Carly, John | 2025-03-06 | 2025-03-17 | Sprint 11 | In Progress | 4
Update Camera Mount Angles on TopBack Part | Aidan, Carly, John | 2025-03-06 | 2025-03-17 | Sprint 11 | In Progress | 5
Sponsor Meeting | Aidan, Carly, Diego, John, Matthew, Amber | 2025-03-19 | 2025-03-19 | Sprint 11 | Todo | 0.5
3D-Print CASA 6.0 | Aidan, Carly, John, Amber | 2025-03-16 | 2025-03-19 | Sprint 11 | In Progress | 2
Refine and Change CASA 6.0 as Needed | Aidan, Carly, John | 2025-03-19 | 2025-03-21 | Sprint 11 | In Progress | 4
Re-Print CASA 6.0 (if needed) | Aidan, Carly, John, Amber | 2025-03-19 | 2025-03-24 | Sprint 11 | In Progress | 5
Enviornmental Tests | Aidan, Carly, Diego, John, Matthew, Amber | 2025-03-21 | 2025-03-25 | Sprint 11 | Done | 1
Camera view SRVM | Aidan, Carly, Diego, John, Matthew, Amber | 2025-03-21 | 2025-03-25 | Sprint 11 | Todo
Functionality Verification SRVM | Aidan, Carly, Diego, John, Matthew, Amber | 2025-03-21 | 2025-03-25 | Sprint 11 | Todo
Sponsor meeting | Aidan, Carly, Diego, John, Matthew, Amber | 2025-03-26 | 2025-03-26 | Sprint 11 | Done | 0.5
Award Nominations | Carly | 2025-03-27 | 2025-03-31 | Sprint 11 | Done | 4
Email Sponsor | Carly | 2025-03-25 | 2025-03-31 | Sprint 11 | Done | 0.5
3D print | Carly | 2025-03-25 | 2025-04-01 | Sprint 11 | Done | 3
Purchase Necessary Diorama Pieces | Aidan, Carly, Diego, John | 2025-04-01 | 2025-04-02 | Sprint 11 | Todo | 0.5
[5 empty] | Total Hours | 32.5 | Total Tasks | 16

## Matthew_Sprint_11
Task | Assignees | Start date | End date | Sprint | Status | Hours Completed | Corrective Action
Pick Fan for Heat Management | Aidan, Carly, Diego, John, Matthew, Amber | 2025-03-06 | 2025-03-09 | Sprint 11 | Done | 0.5
360 Degree Birds eye view VTP | Aidan, Carly, Diego, John, Matthew, Amber | 2025-03-03 | 2025-03-14 | Sprint 11 | Todo | 2
Camera Stitching Verification | Matthew | 2025-03-05 | 2025-03-14 | Sprint 11 | Todo | 2
Real-Time View Update VTP | Matthew | 2025-03-06 | 2025-03-14 | Sprint 11 | Todo | 2
Sponsor Meeting | Aidan, Carly, Diego, John, Matthew, Amber | 2025-03-19 | 2025-03-19 | Sprint 11 | Todo | 0.5
Object Detection & Labeling VTP | Matthew, Amber | 2025-03-14 | 2025-03-21 | Sprint 11 | In Progress | 2
Enviornmental Tests | Aidan, Carly, Diego, John, Matthew, Amber | 2025-03-21 | 2025-03-25 | Sprint 11 | Done | 1
Camera view SRVM | Aidan, Carly, Diego, John, Matthew, Amber | 2025-03-21 | 2025-03-25 | Sprint 11 | Todo
Functionality Verification SRVM | Aidan, Carly, Diego, John, Matthew, Amber | 2025-03-21 | 2025-03-25 | Sprint 11 | Todo
Sponsor meeting | Aidan, Carly, Diego, John, Matthew, Amber | 2025-03-26 | 2025-03-26 | Sprint 11 | Done | 0.5
Simplify rendering hot loop | Matthew |  |  | Sprint 11 | Done | 15
Migrate Loader to seperate crate | Matthew |  |  | Sprint 11 | Done | 2
Simplify smpgpu typed buffers | Matthew |  |  | Sprint 11 | Done | 4
Make UI buttons switch views | Matthew |  |  | Sprint 11 | Done | 3
Add frame rate limiter | Matthew |  |  | Sprint 11 | Done | 0.5
[5 empty] | Total Hours | 35 | Total Tasks | 15

## Aidan_Sprint_11
Task | Assignees | Start date | End date | Sprint | Status | Hours Completed | Corrective Action
Pick Fan for Heat Management | Aidan, Carly, Diego, John, Matthew, Amber | 2025-03-06 | 2025-03-09 | Sprint 11 | Done | 0.5
360 Degree Birds eye view VTP | Aidan, Carly, Diego, John, Matthew, Amber | 2025-03-03 | 2025-03-14 | Sprint 11 | Todo | 2
Update Nose, BottomMiddle, TopMiddle, BottomBack, and Wing Parts to Incorporate Fan and Reduce Blind Spots | Aidan, Carly, John | 2025-03-06 | 2025-03-17 | Sprint 11 | In Progress | 4
Update Camera Mount Angles on TopBack Part | Aidan, Carly, John | 2025-03-06 | 2025-03-17 | Sprint 11 | In Progress | 5
Sponsor Meeting | Aidan, Carly, Diego, John, Matthew, Amber | 2025-03-19 | 2025-03-19 | Sprint 11 | Todo | 0.5
3D-Print CASA 6.0 | Aidan, Carly, John, Amber | 2025-03-16 | 2025-03-19 | Sprint 11 | In Progress | 2
Refine and Change CASA 6.0 as Needed | Aidan, Carly, John | 2025-03-19 | 2025-03-21 | Sprint 11 | In Progress | 4
Re-Print CASA 6.0 (if needed) | Aidan, Carly, John, Amber | 2025-03-19 | 2025-03-24 | Sprint 11 | In Progress | 5
Enviornmental Tests | Aidan, Carly, Diego, John, Matthew, Amber | 2025-03-21 | 2025-03-25 | Sprint 11 | Done | 1
Camera view SRVM | Aidan, Carly, Diego, John, Matthew, Amber | 2025-03-21 | 2025-03-25 | Sprint 11 | Todo
Functionality Verification SRVM | Aidan, Carly, Diego, John, Matthew, Amber | 2025-03-21 | 2025-03-25 | Sprint 11 | Todo
Sponsor meeting | Aidan, Carly, Diego, John, Matthew, Amber | 2025-03-26 | 2025-03-26 | Sprint 11 | Done | 0.5
Purchase Necessary Diorama Pieces | Aidan, Carly, Diego, John | 2025-04-01 | 2025-04-02 | Sprint 11 | Todo | 0.5
[5 empty] | Total Hours | 25 | Total Tasks | 13

## John_Sprint_11
Task | Assignees | Start date | End date | Sprint | Status | Hours Completed | Corrective Action
Pick Fan for Heat Management | Aidan, Carly, Diego, John, Matthew, Amber | 2025-03-06 | 2025-03-09 | Sprint 11 | Done | 0.5
360 Degree Birds eye view VTP | Aidan, Carly, Diego, John, Matthew, Amber | 2025-03-03 | 2025-03-14 | Sprint 11 | Todo | 2
Update Nose, BottomMiddle, TopMiddle, BottomBack, and Wing Parts to Incorporate Fan and Reduce Blind Spots | Aidan, Carly, John | 2025-03-06 | 2025-03-17 | Sprint 11 | In Progress | 4
Update Camera Mount Angles on TopBack Part | Aidan, Carly, John | 2025-03-06 | 2025-03-17 | Sprint 11 | In Progress | 5
Sponsor Meeting | Aidan, Carly, Diego, John, Matthew, Amber | 2025-03-19 | 2025-03-19 | Sprint 11 | Todo | 0.5
3D-Print CASA 6.0 | Aidan, Carly, John, Amber | 2025-03-16 | 2025-03-19 | Sprint 11 | In Progress | 2
Refine and Change CASA 6.0 as Needed | Aidan, Carly, John | 2025-03-19 | 2025-03-21 | Sprint 11 | In Progress | 4
Re-Print CASA 6.0 (if needed) | Aidan, Carly, John, Amber | 2025-03-19 | 2025-03-24 | Sprint 11 | In Progress | 5
Enviornmental Tests | Aidan, Carly, Diego, John, Matthew, Amber | 2025-03-21 | 2025-03-25 | Sprint 11 | Done | 1
Camera view SRVM | Aidan, Carly, Diego, John, Matthew, Amber | 2025-03-21 | 2025-03-25 | Sprint 11 | Todo
Functionality Verification SRVM | Aidan, Carly, Diego, John, Matthew, Amber | 2025-03-21 | 2025-03-25 | Sprint 11 | Todo
Sponsor meeting | Aidan, Carly, Diego, John, Matthew, Amber | 2025-03-26 | 2025-03-26 | Sprint 11 | Done | 0.5
Wrote Nomination for Video | John | 2025-03-25 | 2025-03-30 | Sprint 11 | Done | 1
Made Engines Smaller | John | 2025-03-25 | 2025-04-01 | Sprint 11 | Done | 0.5
Printed Re-Designed Tail, Elevator, and Camera Cases | John | 2025-03-25 | 2025-04-01 | Sprint 11 | Done | 0.5
Made Wings Thinner | John | 2025-03-25 | 2025-04-01 | Sprint 11 | Done | 1
Fixed Rear Camera Case Tolerances | John | 2025-03-06 | 2025-04-01 | Sprint 11 | Done | 0.5
Re-Designed Tail and Elevator w/ Angle Change | John | 2025-03-25 | 2025-04-01 | Sprint 11 | In Progress | 3
Purchase Necessary Diorama Pieces | Aidan, Carly, Diego, John | 2025-04-01 | 2025-04-02 | Sprint 11 | Todo | 0.5
[5 empty] | Total Hours | 31.5 | Total Tasks | 19

## Team Summary
Team Member | Task | Hours
Amber | 13 | 23
John | 19 | 31.5
Carly | 16 | 32.5
Aidan | 13 | 25
Matthew | 15 | 15
Diego | 11 | 8.5